Problem 1

Part-a

Part-b

| Index | Optimistic | Pessimistic | Most Likely | Mean Time (Weeks) | Variance |
| --- | --- | --- | --- | --- | --- |
| A | 1 | 3 | 2 | 2 | 0.111111 |
| B | 2 | 8 | 3.5 | 4 | 1 |
| C | 6 | 18 | 9 | 10 | 4 |
| D | 4 | 10 | 5.5 | 6 | 1 |
| E | 1 | 5 | 4.5 | 4 | 0.444444 |
| F | 4 | 10 | 4 | 5 | 1 |
| G | 5 | 11 | 6.5 | 7 | 1 |
| H | 5 | 17 | 8 | 9 | 4 |
| I | 3 | 9 | 7.5 | 7 | 1 |
| J | 3 | 9 | 9 | 8 | 1 |
| K | 4 | 4 | 4 | 4 | 0 |
| L | 1 | 7 | 5.5 | 5 | 1 |
| M | 1 | 3 | 2 | 2 | 0.111111 |
| N | 5 | 9 | 5.5 | 6 | 0.444444 |

The mean is (Optimistic + Pessimistic + 4*Most Likely)/6 and the variance is

((Pessimistic – Optimistic)/6)^2

Part-c

Part-d

The critical path is

ABDGJKL =2+4+6+7+8+4+5= 36

The next critical path is

ABDEIKL = 2+4+6+4+7+4+5 = 32

Part-e

P(X < 47) = P(Z < (47 – 36)/sqrt(5.1111)) = P(Z < 4.87) = 1 (almost 1)

Part-e

P(X < 47) = P(Z < (47 – 36)/sqrt(5.1111)) = P(Z < 4.87) = 1 (almost 1)

Part-f

P(X < 43) = P(Z < (43 – 36)/sqrt(5.1111)) = P(Z < 3.10) = 0.9990

Problem  2

Part-a

ABCDGHM = 2+4+10+6+7+9+2=40

ABCEHM = 2+4+10+4+9+2=31

ABCEFJKN = 2+4+10+4+5+8+4+6=  43

ABCEFJLN = 2+4+10+4+5+8+5+6 = 44

ABCIJKN = 2+4+10+7+8+4+6= 41

ABCIJLN = 2+4+10+7+8+5+6 = 42

| Length of Path |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ABCDGHM | ABCEHM | ABCEFJKN | ABCEFJLN | ABCIJKN | ABCIJLN |
| 40 | 31 | 43 | 44 | 41 | 42 |

Part-b

The critical path is ABCEFJLN = 2+4+10+4+5+8+5+6 = 44

We apply the marginal cost analysis

The smallest crash cost per week saved is activity J which is on the critical path

|  |  | Length of Path |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Crash Activity | Cost Involved in Crashing | ABCDGHM | ABCEHM | ABCEFJKN | ABCEFJLN | ABCIJKN | ABCIJLN |
|  |  | 40 | 31 | 43 | 44 | 41 | 42 |
| J | $ 30,000 | 40 | 31 | 42 | 43 | 40 | 41 |

ABCEFJLN = 43 is still the critical path, so the activity to crash in the next step is J

|  |  | Length of Path |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Crash Activity | Cost Involved in Crashing | ABCDGHM | ABCEHM | ABCEFJKN | ABCEFJLN | ABCIJKN | ABCIJLN |
|  |  | 40 | 31 | 43 | 44 | 41 | 42 |
| J | 30,000 | 40 | 31 | 42 | 43 | 40 | 41 |
| J | 30,000 | 40 | 31 | 41 | 42 | 39 | 40 |

ABCEFJLN = 42 is still the critical path and the next activity to crash is Activity F (cost = $40,000) since we  J cannot be shortened further

|  |  | Length of Path |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Crash Activity | Cost Involved in Crashing | ABCDGHM | ABCEHM | ABCEFJKN | ABCEFJLN | ABCIJKN | ABCIJLN |
|  |  | 40 | 31 | 43 | 44 | 41 | 42 |
| J | 30,000.00 | 40 | 31 | 42 | 43 | 40 | 41 |
| J | 30,000.00 | 40 | 31 | 41 | 42 | 39 | 40 |
| F | 40,000.00 | 40 | 31 | 40 | 41 | 39 | 40 |

ABCEFJLN = 41 is still the critical path and the next activity to crash is Activity F (cost = $40,000)

|  |  | Length of Path |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Crash Activity | Cost Involved in Crashing | ABCDGHM | ABCEHM | ABCEFJKN | ABCEFJLN | ABCIJKN | ABCIJLN |
|  |  | 40 | 31 | 43 | 44 | 41 | 42 |
| J | 30,000.00 | 40 | 31 | 42 | 43 | 40 | 41 |
| J | 30,000.00 | 40 | 31 | 41 | 42 | 39 | 40 |
| F | 40,000.00 | 40 | 31 | 40 | 41 | 39 | 40 |
| F | 40,000.00 | 40 | 31 | 39 | 40 | 39 | 40 |

We have a cost of 30,000 + 30,000 + 40,000+  40,000 = 140,000 associated with reducing the duration by 4 weeks

Problem 3

Part-a

Part-b

SV $ = BCWP – BCWS  = 50 – 25  = 25

SV % = SV$ / BCWS =   25/25 = 1 or 100%

Since SV is positive, the project is ahead of schedule on 5/4/2020

Part-c

CV $ = BCWP – ACWP = 50 – 55 = -5 which  is negative, therefore the cost is above budget or overrun

Part-d

SPI = BCWP/BCWS = 50/25 =  2 which exceeds 1 so project is ahead of schedule