Communication Plan for Emergency Department Nurse Mentorship Project

Project Team Member/Stakeholder; Communication* Preferred Format; Timing; Report Prepared by. Project Sponsor; 1)Project Status Report --In Person 2) Project Progress Report --Email; 1) Monthly 2) Weekly; 1)-Project Manager 2)- Project Manager. Mentorship Coordinator; 1) Progress Report --in person 2) Training Sessions with Nurse Builders (vendor)—In person group event 3)-Training with Laerdal Simulation (vendor)—Group Activity, in person; 1)-Twice/week 2)- Daily for six weeks (per contract) 3)- Daily for three days (per contract); 1)- Verbal status report presented to Project Manager by Mentorship Coordinator 2)- Verbal status report to be addressed with Project Manager at routine twice per week meeting 3)- Verbal status report given to Project Manager at routine twice/week meeting. E.D. Nurse Mentors; 1)-Progress Report --in person 2)- Training Sessions with NurseBuilders (vendor)—in person group event; 1)- Weekly 2)- Twice per week for six weeks (two RNs per class, per day); 1)- Verbal status report by ED Nurse Mentors given to Project Manager during weekly progress meeting 2)- Training interaction to acquire competency; progress to be shared with Project Manager at weekly meetings. E.D. Physicians E.D. Physicians; 1)-Plan Overview with Discussion of Expectations—in person 2)- Plan Progress Report—Email; 1)- One week preceding plan implementation 2)- Weekly; 1)- Verbalized to ED physicians by Project Manager to encourage Q&A. 2)- Formal Email composed by Project Manager addressing E.D. Physicians. E.D. Staff Nurses (non-mentors); 1)- Plan Overview with Discussion of Expectations—In person 2)- Plan Progress Report—In person 3)- Whiteboard-led Huddle discussion—group activity, in person; 1)- Week preceding plan implementation 2)- Weekly 3)- Weekly; 1)-Project Manager 2)-Project Manager 3)- Project Manager, in conjunction with E.D. Manager. E.D. Manager; 1)- Collaborative planning meetings—in person 2)- Plan Progress Report—In person 3)- Whiteboard Installation Meeting—in person 4)- Training with Laerdal Simulation (vendor) 5)- Training Sessions with Nurse Builders (vendor)—in person group event; 1)- Weekly prior to plan implementation 2)- Twice per week following implementation 3)- Upon arrival (ordered) 4)- Daily for three days (per contract) 5)- Twice per week for six weeks; 1)- Led by Project Manager, with stakeholder collaboration 2)- Verbal exchange of information between Project Manager and E.D. Manager 3)- Project Manager, collaboratively with IT and Quality Manager 4)- Training interaction to acquire competency 5)-Training interaction to acquire competency. Clinical Education Facilitator Clinical Education Facilitator; 1)- Collaborative planning meetings—in person 2)- Training with Laerdal Simulation (vendor) 3)- Training Sessions with Nurse Builders (vendor)—in person group activity; 1)- Weekly prior to plan implementation 2)- Daily for three days (per contract) 3)- Twice per week for six weeks; 1)- Led by Project Manager 2)- Training interaction to acquire competency 3)- Training interaction to acquire competency. Unit Clerk; 1)- Plan Overview with Discussion of Expectations—In person; 1)-Week preceding plan implementation; 1)-E.D. Manager. Information Technology Department; 1)- Whiteboard Installation Meeting—in person 2)- Training with Laerdal Simulation (vendor)—In person group activity; 1)- Upon arrival of whiteboard 2)- Daily for three days (per contract); 1)- Project Manager, in conjunction with E.D. Manager 2)- Training interaction to acquire competency (I.T. will provide ongoing support for simulation equipment). Quality Manager; 1)-Whiteboard Installation Meeting—in person; 1)-Upon arrival of whiteboard; 1)-Project Manager, in conjunction with E.D. Manager and I.T. staff. Human Resources; 1)- Plan Overview with Discussion regarding personnel ramifications—in person; 1)-Week preceding plan implementation; 1)- Project Manager, with Mentorship Coordinator and E.D. Manager. Risk Management; 1)- Plan Overview with Discussion of Expectations—Email, Webex if requested; 1)-Week preceding plan implementation; 1)- Project Manager, with E.D. Manager. Marketing Department; 1)-Plan Overview with Discussion of Expectations—in person 2)- Job Fair discussion—In person 3)- Advertisement of Mentorship Training Opportunity—Email, Webex; 1)- Week preceding plan implementation 2)- Following project plan implementation 3)- Following project plan implementation; 1)-Project Manager, with assistance of E.D. Manager and Mentorship Coordinator 2)- Project Manager, E.D. Manager, and Mentorship Coordinator 3)- Project Manager, Human Resources Director.