## Slide 1
Chapter 2.5
Estimating Project Costs to Determine and Confirm Scope and Approach

## Slide 2
Costing has multiple purposes:
Determine project feasibility
Plan and achieve costs within needed range
Develop and refine planned approach
Monitor and control project execution

## Slide 3
Approximate costs are needed to determine feasibility and initiate project
Expert judgment
Analogous estimating
Parametric estimating

## Slide 4
Plus or minus 15% frequently largest permissible variation
Owners and financiers will make go-or-no go decisions based on these costs
These costs can influence and help establish GMP (guaranteed maximum price)
Approximate costs must be believable and fairly precise

## Slide 5
Bottom-up Estimates Require Professional Skill and Knowledge

## Slide 6
Early completeness essential
Early precision less critical
WBS (work breakdown structure) is established early
CSI (Construction Specification Institute) master format system widely used
An organizational system is needed so nothing is missed

## Slide 7
A reusable template aids efficiency and completeness
A reusable template forces a structured, methodical approach
Firm’s templates are a valuable process asset and competitive advantage
Summary templates: 1 page small projects, 2-3 pages large projects
Summary supported by detail on additional pages

## Slide 8
Standard measurement units must be used
All items must be counted and measured
Initial counting and measuring must be accurate and precise
Initial unit costs are less precise, and must be fine tuned later
Component costs are broken down: labor, material, subcontractors and vendors

## Slide 9
Labor unit cost starts with man-hours, adds money later
Baseline labor productivity rates taken from cost library
Rate adjusted for productivity of intended project approach
Further adjusted for high, confined or congested spaces
Hourly cost, including burdens, are then applied

## Slide 10
Material costing also starts with cost library, then is adjusted
Accurately count and measure all components
Add general or component specific waste factors
Include unit costs from cost library
Precision of estimate is not suitable for material ordering

## Slide 11
Subcontractor and vendor estimating is similar
Estimate subcontractor work the same as self performed work
Finds mistakes, opportunities for improvement
Subcontractor bids are then obtained and analyzed
Keeps subs honest and improves negotiations

## Slide 12
After permanent building is costed, GCs (general conditions) are costed
Good knowledge of permanent building improves GC development
Some CM contracts mandate early fixed GC cost
GCs must be both accurate and acceptable to project owner
GC items may be correctly estimated, then renamed and reallocated for owner acceptance

## Slide 13
Cost Libraries are Essential for Estimating

## Slide 14
Library assembly is slow and tedious,
but not hard
Components organized in same manner as estimate
Standard units of measure are used
Delivery charges and sales tax are included

## Slide 15
Library is a firm’s asset that is continually refined
Baseline of past projects initially assembled
Monitoring and controlling work performed suggests adjustments
Subs may perform a single item, or provide credible unit costs
Estimating speed and accuracy continually improves

## Slide 16
Burdens must be accurate
Government or insurance mandated costs
Pension, health, union, dues
Internal costs, such as small tools and vehicle expense
Burdens, a huge project cost, must be controlled and managed

## Slide 17
Burdens must be customary and acceptable to project owner
Compatible with construction manager’s accounting system
Understandable to project owner
Owners may have an emotional reaction to some burdens
Recasting, renaming and reallocating may be required

## Slide 18
Estimate permanent building the way you build
Prepare estimate in order of installation
Think in systems: “how does it work?”, “what holds it up?”, how is this powered?
Build it “in your head and on paper”
Don’t stop until it makes sense

## Slide 19
Compare expected with estimate results
Ratios of material to labor cost by component
Man-hours per square foot or percent of total cost
Original order of magnitude cost to precisely estimated cost
Find errors and needed adjustments

## Slide 20
Value engineering and process improvement accelerated
Needed cost savings rapidly investigated
Evaluation of cost-effectiveness of planned approach
Superintendent’s understanding and suggested improvements
Consistent approach makes suggestions believable to project owner

## Slide 21
Estimate’s WBS quantities and cost and schedule control
Detailed costs used for financial accounting
Detailed costs used for cost accounting, monitoring and controlling
Quantities imported into project schedule
Estimate is baseline for future change management