## Slide 1
Chapter 2.7
Time is Continuous and Has Costs and Impacts

## Slide 2
Time is measured directly and by its impact
Time measured and managed with schedules
    Scope or cost changes affect time
    Time affects scope and cost

## Slide 3
Time periods must align with the project and needs of the owner

## Slide 4
Seconds, minutes, hours, days, weeks, months
Time periods should be consistent with the duration
  Do not use minutes to describe durations that would take days to complete
Those time periods should be used consistently
  Do not use days to describe one activity and hours to describe another
  It is appropriate to describe time periods differently for milestones versus individual activities, etc.
Select the standard unit of time measurement appropriate

## Slide 5
Time periods must have meaning to many
One week is a standard period to accounting & payroll
  Some payroll based on two weeks, or twice per month
  Accounting reporting is also typically made in quarters
One day is a standard period for individual construction activities, weeks for milestones

## Slide 6
Drop dead dates –
  Owner: “The store must be open by this date”
    May have liquidated damages
  General Contractor: “We must complete all of the foundations by this date”
Project start date
  Best practice is to have fully executed contract, but if all parties are in agreement, a notice to proceed may suffice while fine details are worked out
Relevant time periods established by project participants

## Slide 7
The Cost and Value of Time

## Slide 8
Time produces ongoing cost
Personnel and equipment assigned to project have continual costs
Project owners pay interest on construction loan
  If move-in is delayed, they may also have to extend their current lease

## Slide 9
Time’s passage continually eliminates project options
Mid-project change to new sequence may be cost prohibitive or impossible
Less desirable but more costly sequences may be forced
  Move to a 2 shift or 3 shift model – continuous construction

## Slide 10
Momentum increases productivity
Most construction companies favor a fast pace
    Their hourly employees may not
Chemical cure times must be observed
Safe and productive jobsite density limits observed
    Diminishing rate of production with too much manpower, means you will pay more for completing that task, but overall duration reduced

## Slide 11
High productivity expectations increase momentum
A fast-pace focuses on task execution
Incentive to work out small coordination details immediately
Communication improved and management time reduced

## Slide 12
Time measurement and management is a foundation of cost and schedule control
These concepts seem elementary and obvious, but they are the foundation of project success.