## Slide 1
Chapter 2.8
Scheduling and Time Planning also Adjusts and Confirms the Scope and Approach

## Slide 2
Time planning and scheduling starts in planning
Balance of scope, time and cost must be established early (triple constraint)
Obstacles, scarce resources and risks identified
Specific determination and verification for each project required
    Past experience and rules of thumb are not enough

## Slide 3
Time approximation and feasibility evaluated first
Order of magnitude estimates, similar to costing, are used
Time approximations less precise than material cost approximations
  Too many factors to consider relating to production rates, seasons, late delivery of material, etc.

## Slide 4
Building the Schedule to Implement and Communicate
the Plan

## Slide 5
Estimate identifies activities and establishes WBS (work breakdown structure)
Estimate produces valuable quantitative data
Estimate data then exported to schedule
Scheduling in construction starts after cost estimate is started

## Slide 6
Activities identified, relationships defined & resources assigned
Resulting schedule and project duration produced
Scheduling tools show if estimated decisions achieve workable purpose

## Slide 7
Activities definition must be complete and aid communication
Activities include permissions, engineering, procurement & construction
Activities must show relevance to other activities
  What needs to happen before something else does. Lots of acceptable scenarios, but does it make sense?
Summarize and state activities to communicate to multiple parties
  Don’t use “finish walls” to describe: tape & bed / prime / paint all in one activity

## Slide 8
Every activity has at least one predecessor and one successor (except for the very first and last activity)
Specify most critical activity relationships
“Everything is related” has no meaning
  Don’t tie one activity with every single successor, it just makes reconciling the schedule more difficult
Set activities in order – essential relationships determined

## Slide 9
Activity list sequence and grouping can improve communication
Listing activities in sequence of execution is normal and good.
Meaningful groupings aid analysis and communication

## Slide 10
Start and finish relationships must be real and manageable
Finish to start – the common flexible schedule workhorse
Finish to finish
Start to start
Start to finish

## Slide 11
Activity Resources Relate
Cost to Time

## Slide 12
Resource calendars define personnel working time limits
Working days and times established
Must be realistic, including project area work customs
Calendar must match costs included in estimate
Unbudgeted overtime in schedule is common error

## Slide 13
Equipment and material can be assigned as resources
Large, scarce equipment can be an assigned resource
  Tower crane
Small tools and equipment are not assigned resources

## Slide 14
Using the Schedule for
Needed Approach Correction

## Slide 15
Schedule shows impact of previous decisions and assumptions
Initial schedule may not produce desired project duration
Schedule improvement by adjustment of resources and relationship possible

## Slide 16
Float can be adjusted to act as a shock absorber
Activities on critical path have no float
Activities not on critical path have some float

## Slide 17
Overlap activities – adjust lead and lag times
Some overlap is realistic and achievable
Practical field knowledge defines limits

## Slide 18
Fast tracking
Entire phases of project may be overlapped
  Can design, permit and start foundation before rest of the structure is designed
Considerable management time and judgment required
Risk increases, and cost can increased

## Slide 19
Resources can be altered
Resources can be added (but within REALISTIC limits)
Resource calendars can be altered – but probably will affect cost
“Crashing the schedule” – quality and cost can both suffer