# Work Breakdown Structure (WBS)

# Project estimate 6 months

# Date

Project Name: Manage Your Health, Inc. (MYH)

Project estimate: 6 months

- Preparation and Inception (31 days)- Budget $100,000

  - Team building (3 days) $500

    - Identifying teams’ strengths (Tony Prince)

    - Appointing members to supervise subdepartments (Tony Prince)

    - Identifying tasks and obligations of each team member (Tony Prince)

  - Planning (15 days) $1500

    - Holding participatory discussions (All team members)

      - Drafting the findings to accommodate teams’ ideas (Tonny Prince)

      - Encouraging participation and incorporating all teams’ ideas (Tonny Prince)

    - Constructing timetables and work schedules (all members).

    - Determining and gathering resources required (All members)

  - Budgeting (6 days) $200

    - Constructing a budget for each activity (All members).

  - Sourcing (Tonny Prince); (7 days) $97,800

- Market research and initial testing (50 days) $35,000

  - Product testing (15 days) $5,000

    - Accessing initial customer feedbacks (team A)

    - Giving free trials to customers (team A)

2.2 Product research (5 days) $10,000

    - Conduct research (5 days) (Team A)

      - Research should be anchored upon customer feedbacks for betterment of the services.

  - Advertisement (30 days) $20,000

      - Social media adverts, (team A)

      - Tv commercials (team A)

- Actual product testing (87 days) $50,000

  - Prototyping (30 days) $10,000

    - Product validation and restructuring (Team B)

  - Product costing (1 day) (Team B) $200

  - Commercialization and dissemination (30 days) (Team B) $10,800

  - Product marketing (26 days) (Team B) $29,000

- Monitoring and Evaluation (20 days)

  - Evaluating targets as per criteria (10 days) $5,000

    - Reporting on the project’s overall achievements (Team C)

  - Project Monitoring (10 days) (Team C) $10,000