## Sheet1
Project Name | Time Management
Project Manager | Scott David
Project Deliverable
Start Date | 2021-05-05
End Date | 2021-05-30
Overall Progress | 30%
Activity | Persons Responsible | Start | End | Days | Status | 2021-05-05 | 2021-05-06 | 2021-05-07 | 2021-05-08 | 2021-05-09 | 2021-05-10 | 2021-05-11 | 2021-05-12 | 2021-05-13 | 2021-05-14 | 2021-05-15 | 2021-05-16 | 2021-05-17 | 2021-05-18 | 2021-05-19 | 2021-05-20 | 2021-05-21 | 2021-05-22 | 2021-05-23 | 2021-05-24 | 2021-05-25 | 2021-05-26
1 out of 10
Kick off mtg | Scott David | 2021-05-05 | 2021-05-05 | 0 | Complete
Outline objectives | Brian Atkins | 2021-05-06 | 2021-05-07 | 2 | Complete
Initiation
Detailed Info | Kirk Mike | 2021-05-08 | 2021-05-10 | 3 | Complete
Staffing | Kevin Right | 2021-05-11 | 2021-05-13 | 3 | In progress
Resource Type
Technical Assistance | Kelly Wright | 2021-05-14 | 2021-05-15 | 2 | Not yet St.
complete D | Mousa Will | 2021-05-16 | 2021-05-17 | 2 | Not yet St.
Crashing
Approving O.Time | Anthony Blair | 2021-05-18 | 2021-05-20 | 3 | Not yet St.
Delivery Activities | Lessy Joey | 2021-05-21 | 2021-05-22 | 2 | Not yet St.
Tracking
New logo | Ashley Walters | 2021-05-23 | 2021-05-24 | 2 | Not yet St.
Web Design | Milton Junior | 2021-05-24 | 2021-05-26 | 3 | Not yet St.