## Activities in Gantt Chart
Mobile Health Service Project Timeline
[5 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | Actual (beyond plan)
| Planned | Planned | ACTUAL | ACTUAL
ACTIVITY | START | DURATION | START | DURATION | Months
| Month | Months | Month | Months | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Market research and Purchase mobile van | 1 | 1
Identify the target community | 1 | 1
Purchasec all equipments needed to make convert the mobile van into a point of healthcare delivery | 2 | 1
Purchase and equip the van with the required drugs | 3 | 1
Seek relevant licenses to run the mobile clinic | 4 | 1
sensitize the community about the pending project | 4 | 1
Sought out the personne to run the clinic | 5 | 1
Launch the Project and run it for 6 months | 6 | 12
Evaluate the project's effectiveness in reducing the disease burden in the target community | 10 | 8
How to use this template:
Enumerate your main project activities (rename what you see to define the activities)
Estimate when they need to start
Estimate when they need to end
Track actual start and stop dates as they occur
The chart will populate on what you enter… add lines as needed for activities
Change "Name of Project" to title of your project