## Project Planner
Project Planner |  |  |  |  | A/V Installation | [5 empty] | Period is in Weeks
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Design layouts | 1 | 2 | 1 | 2 | 100%
Prepare drawings, including wiring diagrams | 3 | 3 | 3 | 3 | 100%
Approvals, permits, secure budgets | 6 | 2 | 6 | 2 | 100% | bar: PERIODS 14 to PERIODS 20
Start constructing the building. | 9 | 24 | 9 | 23 | 104% | bar: PERIODS 14 to PERIODS 20
Roofing | 33 | 4 | 33 | 5 | 80% | bar: PERIODS 14 to PERIODS 20
install conduit work and wiring | 39 | 3 | 39 | 3 | 100%
Start Plastering | 43 | 6 | 43 | 5 | 120%
Painting | 49 | 5 | 49 | 6 | 83.33%
Cleaning & carpeting | 56 | 4 | 56 | 4 | 100%
Install hardware | 61 | 3 | 61 | 3 | 100%
Install computer networked system, plasma screens, projectors, amplifiers (Instruments) | 65 | 3 | 65 | 2 | 150%
Testing & delivery of complete system, including operation manuals and training | 68 | 4 | 68 | 4 | 100%