Alaska Fly-Fishing Expedition*

You are sitting around the fire at a lodge in Dillingham, Alaska, discussing a fishing expedition you are planning with your colleagues at Great Alaska Adventures (GAA). Earlier in the day you received a fax from the president of BlueNote, Inc. The presi- dent wants to reward her top management team by taking them on an all-expense-paid fly-fishing adventure in Alaska. She would like GAA to organize and lead the expedition.

You have just finished a preliminary scope statement for the project (see below). You are now brainstorming potential risks associated with the project.  Use memo format!!!

- Brainstorm potential risks associated with this project. Try to come up with at least five different risks.

- Use a risk assessment form similar to Figure 7.6 to analyze identified risks.

- Develop a risk response matrix similar to Figure 7.8 to outline how you would deal with each of the risks.