## from 1 to 5
DIVISION 1 - GENERAL REQUIREMENTS | PRELIMINERIES 2 GROUND WORK 3 CONCRETE 4 MASONRY, PLASTERING 5 METAL AND TIMBER WORKS 6 ROOFING 7 CIELINGS 8 PAINTING 9 ELECRICAL INSTALLATIONS 10 TENDERER'S ADJUSTMENTS
LABOUR, CAPITAL, LAND
DIVISION 2 - SITE | ACCESS, LOCATION, INSTALLATION
LineNumber | Description | Quantity | Unit | Crew | Daily Output | DURATION DAYS | Labor Hours | Material | Labor | Equipment | Total | Ext. Mat. | Ext. Labor | Ext. Equip. | Ext. Total | Mat. O&P | Labor O&P | Equip. O&P | Total O&P | Ext. Mat. O&P | Ext. Labor O&P | Ext. Equip. O&P | Ext. Total O&P | Labor Type | Data Release | CCI Location | Notes
| Excavation of any soil type according to the elements' dimensions mentioned in the drawings with all required works | M3 | 1900 | 20 | 5 | 24 | 8 | NO | PER HOUR | DUMPERS,EXCAVATORS, | 9500 | NO | 7200 | 650 | 2350 | 10 | 50 | 55 | 110 | 700 | 5006 | 2500 | 67000 | MACHINE | ON NOTES | SITE | Excavation quantities are measured to the faces of concrete members. Rates shall include for all additional excavation required to place the formwork. Excavation for (1) Foundation beam TB1 & TB2
| Backfill at areas as shown on the drawing by using approved | M3 | 700 | 10 | 4 | 18 | 8 | SOIL | PER HOUR | SPADE, SKID STEEL LOADERS | 2800 | 200 | 2160 | 600 | 5700 | 20 | 50 | 63 | 133 | 300 | 5687 | 6750 | 23000 | MACHINE | ENGINEER | SITE | Rates shall include for: levelling, Grading, Trimming,
| excavated material with all required works. This item includes | [25 empty] | Compacting to faces of excavation, keeping sides plumb,
| the backfilling to maintain the required levels of the building as | [25 empty] | backfilling, consolidating and disposing surplus soil.
shown in the drawings, specifications and directed by the
Engineer, using suitable material
(25cm max. each &
compaction test 98% ) according to Eng. instructions and
specifications.
| Ditto but using imported and approved Clean Sand Material. | M3 | 100 | 15 | 4 | 18 | 8 | SAND | HOUR | AS ABOVE | 1080 | 1200 | 730 | 600 | 5400 | 30 | 80 | 34 | 153 | 234 | 2400 | 110 | 532 | C/M | ENGINEER | SITE | 5mm thick sand bedding on hardcore
total
DIVISION 3- CONCRETE
LineNumber | Description | Quantity | Unit | Crew | Daily Output | Duration Days | Labor Hours | Material | Labor | Equipment | Total | Ext. Mat. | Ext. Labor | Ext. Equip. | Ext. Total | Mat. O&P | Labor O&P | Equip. O&P | Total O&P | Ext. Mat. O&P | Ext. Labor O&P | Ext. Equip. O&P | Ext. Total O&P | Labor Type | Data Release | CCI Location | Notes
| Lean Concrete | 10 | ITEM | [23 empty] | Rates shall include for: placing in position; making good
| (a) Quantity is measured to the edges of concrete foundation | [25 empty] | after removal of formwork and casting in all required items
| memebers. Rates shall be inclusive of any additional | [25 empty] | to conform to structural and excavated tolerences
| concrete required to place the formwork. | [25 empty] | (b) Rates shall include making and transporting of formwork,
| 50mm thick lean concrete to bottom of | [25 empty] | oil, nails
| (1) Foundation beam TB1 & TB2 |  | M3 | 30 | 20 | 14 | 5 | SAND,CEMENT | CASUAL | SPADE,MIXER | 6000 | 4000 | 1000 | 9800 | 21000 | 700 | 500 | 230 | 1430 | 320 | 200 | 120 | 640 | CASUAL | ENGINEER | SITE | (c) Mix ratio for reinforced concrete shall be 1:2:3
| Foundations | [25 empty] | and lean concrete shall be 1:2:6 by volume.
| Foundation Pad F1 |  | M3 | 23 | 15 | 16 | 6 | CONCRETE | MACHINE,LABOUR | MIXER | 7000 | 6000 | 2500 | 10000 | 27000 | 900 | 600 | 300 | 1800 | 600 | 400 | 240 | 10240 | CASUAL | ENGINEER | SITE | (d) Rates shall include for: cleaning, fabrication,
| Foundation Beam TB1 & TB |  | M3 | 43 | 20 | 14 | 5 | CONCRETE | MACHINE,LABOUR | MIXER | 5000 | 3000 | 1000 | 9000 | 18000 | 600 | 500 | 200 | 1300 | 400 | 200 | 300 | 900 | CASUAL | ENGINEER | SITE | placing, the provision for all necessary temporary
| Ground floor | [25 empty] | fixings and supports including tie wire and chair
| Columns | [25 empty] | supports, laps and wastage
| (1) C1 Column, 250x250 | 2.6 | M3 | 15 | 20 | 24 | 7 | CONCRETE | MACHINE CASUAL | MIXER | 2000 | 4000 | 1000 | 5000 | 12000 | 110 | 120 | 600 | 830 | 300 | 150 | 100 | 550 | MACHINE | ENGINEER | SITE | (e) All reinforcing bars shall be high strength bars
| (2) C2 Column, 200x200 | 2.5 | M3 | 15 | 20 | 24 | 8 | CONCRETE | MACHINE CASUAL | MIXER | 2000 | 4000 | 1000 | 5000 | 12000 | 110 | 120 | 600 | 830 | 300 | 150 | 100 | 550 | MACHINE | ENGINEER | SITE
Stair & Slab
| (1) Stair & Slab | 10.4 | M3 | 25 | 30 | 28 | 9 | CONCRETE | MACHINE CASUAL | MIXER | 2000 | 5600 | 3000 | 7000 | 17000 | 130 | 170 | 780 | 1080 | 600 | 230 | 200 | 100 | 430 | ENGINEER | SITE | Apply slurry type water proofing to all surfaces of concrete
below ground level in accordance with manufacturer's
instructions.
DIVISION 4 - MASONRY
LineNumber | Description | Quantity | Unit | Crew | Daily Output | DURATION DAYS | Labor Hours | Material | Labor | Equipment | Total | Ext. Mat. | Ext. Labor | Ext. Equip. | Ext. Total | Mat. O&P | Labor O&P | Equip. O&P | Total O&P | Ext. Mat. O&P | Ext. Labor O&P | Ext. Equip. O&P | Ext. Total O&P | Labor Type | Data Release | CCI Location | Notes
| Cement blockwork | [25 empty] | Rates shall include for: cleaning out cavities, forming
| 100 mm wide Cement Solid blocks, laid on and incl. mortar, | [25 empty] | rebated reveals and pointing and cleaning down to reveals
| tie rods, compression joint gap filler, nylon / plastic mesh as | [25 empty] | where necessary; fractional size blocks, all necessary
| specified | [25 empty] | machine cutting, cutting or forming chases or edges of
| Ground Floor | 4.7 | M2 | 13 | 45 | 16 | 8 | CEMENT SAND | MANUAL | AN NOTES | 13500 | 7000 | 2000 | 1000 | 10000 | 450 | 95 | 65 | 660 | 540 | 450 | 430 | 1040 | MANUAL | CONTRACTOR | SITE | floor slabs, cutting or leaving holes and openings as
| 12mm plaster on exterio of walls and concrete faces | 4.7 | M2 | 20 | 37 | 38 | 8 | CEMENT SAND | MANUAL | AN NOTES | 14000 | 8000 | 3000 | 2000 | 13000 | 500 | 30 | 40 | 570 | 300 | 400 | 490 | 1190 | MANUAL | CONTRACTOR | SITE | recesses for and building in pipes, conduits, sleeves and
similar as required for all trades; leaving surfaces rough or
raking out joints for plastering and flashings, bedding
frames or plates, building in joists, bearers or similar,
DIVISION 5 - METALS | [26 empty] | temporary supports to openings, templates, reinforcement in
LineNumber | Description | Quantity | Unit | Crew | Daily Output | DURATION DAYS | Labor Hours | Material | Labor | Equipment | Total | Ext. Mat. | Ext. Labor | Ext. Equip. | Ext. Total | Mat. O&P | Labor O&P | Equip. O&P | Total O&P | Ext. Mat. O&P | Ext. Labor O&P | Ext. Equip. O&P | Ext. Total O&P | Labor Type | Data Release | CCI Location | walls and for all necessary making good
| 50mm dia SS pipe handrail (railing between columns) including all | ITEM | NO | 10 | 5 | 7 | 8 | METAL | CASUAL | HACK SAW | 80000 | 2000 | 3000 | 1000 | 6000 | 100 | 20 | 30 | 150 | 38 | 42 | 40 | 120 | MANUAL | MASON | SITE
| fixings and finishes complete as shown in the drawing | [25 empty] | (a) Rates shall include for: all fabrication work, welding, marking,
drilling for bolts including those securing timbers, steel plates, bolts,
nuts and any type of washer, riveted work, counter sinking and
tapping for bolts or machine screws.
(b) Rates shall include for all polishing and finishing as specified
(c) Rates shall include for fabrication and erection and temporary
supports and fixing into position

## from 6 to 8
DIVISION 6 - WOOD, PLASTICS & COMPOSITES
LineNumber | Description | Quantity | Unit | Crew | Daily Output | DURATION DAYS | Labor Hours | Material | Labor | Equipment | Total | Ext. Mat. | Ext. Labor | Ext. Equip. | Ext. Total | Mat. O&P | Labor O&P | Equip. O&P | Total O&P | Ext. Mat. O&P | Ext. Labor O&P | Ext. Equip. O&P | Ext. Total O&P | Labor Type | Data Release | CCI Location | Notes
50 x 150mm timber ridge members
50 x 100mm timber rafters
| 50 x 35mm timber battens | 270000 | M | 10 | 2700 | 10 | 8 | WOOD | MACHINE | MACHINE | 50000 | 30000 | 3450 | 4500 | 38000 | 30 | 200 | 1200 | 1430 | 3420 | 200 | 600 | 540 | 4760 | CARPENTER | SITE | Timber roof structure, including all fixings and complete
DIVISION 7 – THERMAL AND MOISTURE PROTECTION
LineNumber | Description | Quantity | Unit | Crew | Daily Output | DURATION DAYS | Labor Hours | Material | Labor | Equipment | Total | Ext. Mat. | Ext. Labor | Ext. Equip. | Ext. Total | Mat. O&P | Labor O&P | Equip. O&P | Total O&P | Ext. Mat. O&P | Ext. Labor O&P | Ext. Equip. O&P | Ext. Total O&P | Labor Type | Data Release | CCI Location | Notes
| Rock Wool Insulation | [25 empty] | Rock Wool Insulation
| (1) Rock Wool Insulation with Aluminium foil on both sides, Rates | 5900 | M | 5 | 260 | 17 | 8 | COTTON | MACHINE | M/N | 120000 | 1000 | 1000 | 1800 | 2000 | 1200 | 200 | 2300 | 45000 | 560 | 2000 | 6580 | 90000 | MACHINE | MECHANIC | ONSITE | (1) Rock Wool Insulation with Aluminium foil on both sides, Rates
| shall include for wire mesh, nails, and all necessary fixtures | [25 empty] | shall include for wire mesh, nails, and all necessary fixtures
fix
DIVISION 8 – DOORS AND WINDOWS
LineNumber | Description | Quantity | Unit | Crew | Daily Output | DURATION DAYS | Labor Hours | Material | Labor | Equipment | Total | Ext. Mat. | Ext. Labor | Ext. Equip. | Ext. Total | Mat. O&P | Labor O&P | Equip. O&P | Total O&P | Ext. Mat. O&P | Ext. Labor O&P | Ext. Equip. O&P | Ext. Total O&P | Labor Type | Data Release | CCI Location | Notes
| Supply and install Galvanized Steel Door D1 - 1.60x2.20 two | 15 | NO | 10 | 5 | 5 | 5 | METAL | M/N | NOTES | 3000 | 20000 | 200 | 1700 | 20900 | 200 | 200 | 100 | 500 | 100 | 100 | 100 | 300 | MANUAL | ENGINEER | SITE | DOUBLE DOOR
| leave with all required works | [25 empty] | Supply and install powder coated colored Aluminum profile
| Aluminum Windows: | [25 empty] | window W1 - 2.00x1.00, complete with two sliding leave
| Ditto but for W2 - 1.60x1.00 with two sliding leave complete | 109 | NO | 10 | 9 | 20 | 5 | ALUMINIUM | M/N | NOTES | 70000 | 2000 | 600 | 180 | 2180 | 350 | 500 | 200 | 1050 | 20 | 30 | 10 | 60 | MANUAL | ENGINEER | SITE | complete, glazing, silicone sealant, ironmonger and hardware,
| with all required works | [25 empty] | all and anywhere else, needed, all according to drawings,
specifications, conditions and directed instructions by the
Engineer or his representative

## from 9 to 16
DIVISION 9 - FINISHES
LineNumber | Description | Quantity | Unit | Crew | Daily Output | DURATION DAYS | Labor Hours | Material | Labor | Equipment | Total | Ext. Mat. | Ext. Labor | Ext. Equip. | Ext. Total | Mat. O&P | Labor O&P | Equip. O&P | Total O&P | Ext. Mat. O&P | Ext. Labor O&P | Ext. Equip. O&P | Ext. Total O&P | Labor Type | Data Release | CCI Location | Notes
INTERNAL WALL FINISHES
| 40mm thick 1:4 Cement Sand render to wall | 200 | SM | 6 | 50 | 7 | 8 | CONCRETE | MACHINE,MANUAL | MIXER | 90000 | 3000 | 500 | 6000 | 9500 | 500 | 400 | 300 | 1200 | 50 | 120 | 130 | 300 | MACHINERY | ENGINEER | ONSITE | Painting
| 10mm thick cement screed to Wall | 200 | SM | 7 | 50 | 7 | 9 | CONCRETE | MACHINE,MANUAL | MIXER | 90000 | 3000 | 500 | 6000 | 9500 | 500 | 400 | 300 | 1200 | 50 | 120 | 130 | 300 | MACHINERY | ENGINEER | ONSITE | Prepare and apply three coats first quality plastic
emulsion paint to:-
DIVISION 10 - SPECIALTIES
LineNumber | Description | Quantity | Unit | Crew | Daily Output | Duration Days | Labor Hours | Material | Labor | Equipment | Total | Ext. Mat. | Ext. Labor | Ext. Equip. | Ext. Total | Mat. O&P | Labor O&P | Equip. O&P | Total O&P | Ext. Mat. O&P | Ext. Labor O&P | Ext. Equip. O&P | f | Labor Type | Data Release | CCI Location | Notes
NONE
DIVISION 11 - EQUIPMENT
DIVISION 12 - FURNISHINGS
LineNumber | Description | Quantity | Unit | Crew | Daily Output | DURATION DAYS | Labor Hours | Material | Labor | Equipment | Total | Ext. Mat. | Ext. Labor | Ext. Equip. | Ext. Total | Mat. O&P | Labor O&P | Equip. O&P | Total O&P | Ext. Mat. O&P | Ext. Labor O&P | Ext. Equip. O&P | Ext. Total O&P | Labor Type | Data Release | CCI Location | Notes
DIVISION 13 – SPECIAL CONSTRUCTION
DIVISION 14 – CONVEYING SYSTEMS
LineNumber | Description | Quantity | Unit | Crew | Daily Output | DURATION DAYS | Labor Hours | Material | Labor | Equipment | Total | Ext. Mat. | Ext. Labor | Ext. Equip. | Ext. Total | Mat. O&P | Labor O&P | Equip. O&P | Total O&P | Ext. Mat. O&P | Ext. Labor O&P | Ext. Equip. O&P | Ext. Total O&P | Labor Type | Data Release | CCI Location | Notes
DIVISION 15 - MECHANICAL | Daniel Barlow
LineNumber | Description | Quantity | Unit | Crew | Daily Output | DURATION DAYS | Labor Hours | Material | Labor | Equipment | Total | Ext. Mat. | Ext. Labor | Ext. Equip. | Ext. Total | Mat. O&P | Labor O&P | Equip. O&P | Total O&P | Ext. Mat. O&P | Ext. Labor O&P | Ext. Equip. O&P | Ext. Total O&P | Labor Type | Data Release | CCI Location | Notes
Kitchen Sink
A
| 15mm | 15 | NO | 6 | 3 | 5 | 8 | SINKS,CONCRETE CEMENT | MANUAL | BOLTS | 30000 | 5000 | 3000 | 2000 | 10000 | 500 | 400 | 20 | 920 | 500 | 300 | 200 | 1000 | MANUAL | ENGINEER | SITE | Single bowl, single drainer stainless steel kitchen sink of
| diameter chrome plated sink bib tap, chrome plated | [25 empty] | size 1000 x 500mm
| bottle trap with 75mm deep seal and chain waste fitting. | [25 empty] | complete with chrome plated 40mm
waste fittings, plugs, chain stays, overflow, 1No. 15mm
diameter chrome plated sink bib tap, chrome plated
bottle trap with 75mm deep seal and chain waste fitting
| Curtain Rail | 5 | M | 7 | 3 | 4 | 8 | RAIL | MANUAL | NAIL | 5000 | 700 | 300 | 100 | 11000 | 400 | 100 | 50 | 550 | 200 | 300 | 40 | 540 | MANUAL | CARPENTER | SITE | High quality chrome plated 2000mm long curtain rail
with wall plates and complete with hooks and
rollers and medium quality 1800 x 1500mm shower
curtains
DIVISION 16 - ELECTRICAL
LineNumber | Description | Quantity | Unit | Crew | Daily Output | DURATION DAYS | Labor Hours | Material | Labor | Equipment | Total | Ext. Mat. | Ext. Labor | Ext. Equip. | Ext. Total | Mat. O&P | Labor O&P | Equip. O&P | Total O&P | Ext. Mat. O&P | Ext. Labor O&P | Ext. Equip. O&P | Ext. Total O&P | Labor Type | Data Release | CCI Location | Notes
PVC/SWA/PVC Copper cables per meter
| 25mm sq. 4 core | 500 | LM | 10 | 50 | 10 | 6 | CABLE | MANUAL | CABLES | 90000 | 5000 | 4000 | 4000 | 13000 | 600 | 1000 | 900 | 2300 | 90 | 78 | 76 | 123 | MANUAL | ENGINEER | ONSITE | Lighting points wired in 3x1.5 mm
| 95mm sq. 4 core | 700 | LM | 10 | 50 | 10 | 6 | CABLE | MANUAL | CABLES | 90000 | 5000 | 4000 | 4000 | 13000 | 600 | 1000 | 900 | 2300 | 90 | 78 | 76 | 123 | MANUAL | ENGINEER | ONSITE | 2
PVC/SC cables
drawn in 20 mm Ǿ concealed HG PVC conduits
complete with all necessary accessories but excluding
switches for:
i) One way switching
ii) Two Way with Intermediate Switching

## SUMMARY SHEET
Division | name | Ext. Total | Ext. Total O&P
DIVISION 1 - GENERAL REQUIREMENTS | PRELIMINARIES | 67000 | 20000
DIVISION 2 - SITE | EXCAVATION | 300000 | 30000
DIVISION 3- CONCRETE | FLOORING | 250000 | 40000
DIVISION 4 - MASONRY | WALLS | 200000 | 20000
DIVISION 5 - METALS | COLUMN AND BEAM | 50000 | 40000
DIVISION 6 - WOOD, PLASTICS & COMPOSITES | MATERIALS | 190000 | 2900
DIVISION 7 – THERMAL AND MOISTURE PROTECTION | WOOL | 30000 | 3000
DIVISION 8 – DOORS AND WINDOWS | METAL AND WOOD | 150000 | 350
DIVISION 9 - FINISHES | PLASTERING | 200000 | 2300
DIVISION 10 - SPECIALTIES | NONE | 0 | 2000
DIVISION 11 - EQUIPMENT | MASONRY | 80000 | 10000
DIVISION 12 - FURNISHINGS | CHAIRS | 100000 | 29000
DIVISION 13 – SPECIAL CONSTRUCTION | TILING | 140000 | 280000
DIVISION 14 – CONVEYING SYSTEMS | PLUMBING | 80000 | 2000
DIVISION 15 - MECHANICAL | MACHINE | 200000 | 29000
DIVISION 16 - ELECTRICAL | LIGHTING | 170000 | 2880
|  | 2500000 | 513451
total

## Sheet1
Division | Ext. Total | Ext. Total O&P
DIVISION 1 - GENERAL REQUIREMENTS
DIVISION 2 - SITE
DIVISION 3- CONCRETE
DIVISION 4 - MASONRY
DIVISION 5 - METALS
DIVISION 6 - WOOD, PLASTICS & COMPOSITES
DIVISION 7 – THERMAL AND MOISTURE PROTECTION
DIVISION 8 – DOORS AND WINDOWS
DIVISION 9 - FINISHES
DIVISION 10 - SPECIALTIES
DIVISION 11 - EQUIPMENT
DIVISION 12 - FURNISHINGS
DIVISION 13 – SPECIAL CONSTRUCTION
DIVISION 14 – CONVEYING SYSTEMS
DIVISION 15 - MECHANICAL
DIVISION 16 - ELECTRICAL
Total

## Sheet2
Project | CONFERENCE HALL
Contractor’s | URP
Owner’s | SCHOOL | Verity Contracting Group
Architect’s | AAK | Titles | Names | phone # | Email
|  | Project Manager | JACOBS SIR | 20099
|  | Superintendent | DR. E. W | 28009
|  | Project Engineer | DR. K. ENY | 30099
|  | Scheduler | G TONY | 200008
|  | Estimator | ABHI K. | 29007
|  | Estimator Assistant | PRAGH S. | 40006