## Sheet1
COMMUNICATION MATRIX
project name |  | Getta Bill
Project Manager Name |  | Ima Pyne
Project Description |  | Replacing Billing System
ID | Communication Vehicle |  | Target Audience | Description purpose | Frequency | Sender | Distribution Vehicle | Internal/ External | Comments
0 | weekly status report |  | project team | project status communication update | weekly | John Doe | Email | External and Internal | full team meeting. Stakeholders will be invited when necessary
1 | steering committee |  | Data Engineer, CEO, | Updating the project current status | Monthly | Project | Meeting | Internal | steering committee
| review |  | Sales Director, CFO, |  |  | manager
Project manager,
Finance Director,
Accounting Director,
2 | Weekly status report |  | Project team, CFO, | Current timeline, update status, | Weekly | project | Email | Internal
|  |  | Accounting Director, | planned work, major accomplishment |  | manager
CEO
Finance Director,