## Calculations
Trees Baseline: Planned Value (PV):
| 1000 | 1000 | 1000 | 1000 | 1000
| 1000 | 2000 | 3000 | 4000 | 5000
0 | 1 | 2 | 3 | 4 | 5
Earned Value Using Trees:
Wil has estimated that 6,000 trees have been sheared after 5 workdays. This number
suggests 1,000 more trees sheared than expected through period five. Percent complete at
the end of period 5 is 6,000/5,000 = |  |  |  | 1.2 | or 120 percent of expected.
Cost (tree) Variance: CV = EV – AC
EV = percent complete x planned value = 1.2 x 5,000 = |  |  |  |  | 6000 | trees sheared
CV = 6,000 – 6,000 actual = 0 (for trees)
Schedule (tree) Variance: SV = EV – PV
EV = 1.20% x 5,000 = 6,000 trees |  | 6000 | Trees
SV = 6,000 – 5,000 = +1,000 trees. You are ahead of schedule by 1,000 trees. |  | 1000 | trees. You are ahead of schedule by 1,000 trees.
Earned Value Using Money
Wil has estimated that 6,000 trees have actually been sheared after 5 workdays. This
number suggests 1,000 more trees sheared than expected through period five. Percent
complete at the end of period 5 is 6,000/5,000 = 1.20 or 120%.
Computations using the traditional money budget approach:
Planned Baseline: Budget Values (PV)
| $1250 | $1250 | $1250 | $1250 | $1250
| $1250 | $2500 | $3750 | $5000 | $6250
0 | 1 | 2 | 3 | 4 | 5
Cost Variance: CV = EV – AC
EV = 1.20% x $6,250 = |  | 7500
CV = $7,500 – $7,500 actual = 0 (on cost)
Schedule Variance: SV = EV – PV
EV = 1.20% x $6,250 = $7,500
SV = $7,500 – $6250 = +$1,250 (ahead of schedule)
(Note: $1,250 represent the value of schedule variance of 1,000 trees above)

## Part I
Is Wil over, on, or below cost and schedule? Is Wil using earned value?
Wil is applying the percent complete to the number of trees sheared.
His system is always on cost and on schedule. His system does not allow him to really
compute cost or schedule variance midway in the project.

## Part II
How can Wil set up a scheduling variance?
Earned value requires planned values (PV) of sheared by cost or trees (PV) to be setup on
a timeline. This is the major difference from straight accounting or percent complete
math. The number of trees or dollars planned must be assigned to time periods over the
life cycle of the project. An estimate of percent complete is needed in terms or trees or
money.