Colorado Springs Welcome Home Parade Case

Student name.

Date.

Class.

Scope overview and the business case.

The main objective of this project is to organize a winning parade and welcome for our soldier and also give them tribute for the winning over Iraq in the previous war. The event is held to celebrate the win after the Great War and also give praise to the great soldier of the United States Army and even the air force. The project explains how brave soldier fighting war in Iraq and showing tributes to the fallen soldier who lost their lives for our beloved country. The business case for the event is to organize the event according to the planned budget and demonstrate the parade to the maximum number of resident that will arrive and make the event more successful.

Milestone Schedule and Deliverables. (Ca Blake, K. S. 2002).

| Milestone | Completion Date | Stakeholder | Acceptance Criteria |
| --- | --- | --- | --- |
| Current State |  |  |  |
| Project Proposal | 15/01/04 | The City Council of Colorado Springs | The documents must be reviewed and approved. |
| Approval of the Project | 20/01/04 | The government. | The documents must be reviewed and approved. |
| Assigning Project Management Team | 22/01/04 | assistant city manager | Checking the capability of the members and requirement for the team. |
| Survey of the Venue. | 29/02/04 | The management team. | Inspection of all documentation of the project and the project design. |
| Future State |  |  |  |
| Budget Planning | 10/02/04 | The Management team | Documentation must meet business requirement and approval of the project management. |
| Raising Fund | 29/02/04 | The Management team. | The fund must meet the budget of the project. |
| Project Planning | 24/03/04 | The Management team | To execute the project made as per the survey and documentation of the project design. |
| Planning and collection of resources. | 20/04/04 | The Management team | Documentation must meet the requirement of the project |
| Advertisement | 28/05/04 | Media management team. | All documentation and approval for advertisement must be shown |
| Ultimate Goal Project Execution. | 05/06/04 | All stakeholders | The final execution of the project must show documentation and support by all stakeholders. |

### Risks and Assumptions (Beckius, J., 2002).

| Project Risks and Assumptions | Risk Owner | Contingency Plans |
| --- | --- | --- |
| 1. Traffic controller. | Police department | Controlling traffic and all traffic signal controls. |
| 2. Maintaining schedule and timing | Management Team | Managing the time that is set for the event. |
| 3.Limited time and fund | Management team | Determining how the event will occur. |
| 4. Security and safety | Police department | Proving police official in short intervals |
| 5. Parking and safety | Police department | Packing place provides. |
| 6. Fire and medical. | Fire and medical department | Ambulances, 23 fire trucks, and officials to control any emergency that may occur. |
| 7. Providing food for lunch | Catering Department | Food was obtained from a local restaurant around the place. |

Stakeholders

| Stakeholders | Interest in Project |
| --- | --- |
| Primary: 1. Police Department 2. Fire Department 3. Military Officials. 4. Air force head. 5. Management team | Responsible for controlling Traffic and proving Security Fire and medical safety. Planning and providing enough resources Planning And providing required resources Planning and Finalizing of the project |
| Others: 1. The Local Restaurants 2. The local Park Authority 3. Military Band 4. Transportation Department | Providing food Services Providing Place for Catering Demonstrating the music. Proving the Bus and vehicles for parade. |

Resources Required. (Ca Blake, K. S. 2002).

People. The people that are needed so that the project can finalize successfully are as follows.

Military heads.

Management members.

Police officials.

Air force officers.

Fire officers.

Musical band officers.

Funding. The total amount of money that the event required was $300,000 according to the budget made for the finalizing of the project. The project management is needed to organize a proper budget for the appropriate execution of the project. Good breakdown of the budget structure is provided in part II of the project.

Equipment. Equipment such as chairs, light, cars, ambulance, Musical instrument, and firefighter should be available and provided early enough to minimize delay in the event.

Others. Other resources, such as Food, parking, and place for catering, should be openly known.

Operating principle for all stakeholders.

Maintenance of discipline and punctually.

Being fair, honest, and engage in open communication.

Providing feedback with all stakeholders in the event.

Encouraging performance by praising the performer for their work.

Completed lessons Learned. (Beckius, J. 2002).

- Planning budget.

- Project planning.

- Managing team.

- Raising Funds.

- Conducting event.

- Executing the project.

Commitment.

| Sponsor | Department / Organization | Signature |
| --- | --- | --- |
| Mr. mike James. | The City Council of Colorado Springs and city resources. |  |
| Project Manager | Department / Organization | Signature |
| Jackson Edwin. | O’Donnell & O’Donnell LLP |  |
| Core Team Members | Department/ Organization | Signature |
| Samson fetus. | Management team committee |  |
| Luke Jonathan | Police Department |  |
| Martin Kennedy. | Transport department |  |
| Adeline Simon | Fire and Safety Department. |  |
| Samuel Freddy | Catering department. |  |

Part II

- The budget for successful execution of the event is as follows. (Regni,2009)

| Budget |  |
| --- | --- |
| Particulars | Amount $ |
| chairs | $ 30,000.00 |
| Transportation. | $ 20,000.00 |
| Event Management Teams. | $ 30,000.00 |
| Cleaning Crew | $ 10,000.00 |
| Sound systems | $ 10,000.00 |
| pre event meeting | $ 10,000.00 |
| Fireworks | $ 20,000.00 |
| Team's Fee Lighting | $ 30,000.00 |
| Advertisement | $ 20,000.00 |
| Catering | $ 70,000.00 |
| Decoration | $ 20,000.00 |
| Band | $ 20,000.00 |
| Miscellaneous Expenses | $ 20,000.00 |
| Total Budget | $ 300,000.00 |

- Work Breakdown Structure. (Laine, D.et al 2003)

Colorado Parade.

↓

Planning -Planner -Ideas -Execute plans.

↓

Transportation -Drivers -Vehicles -Transport troops.

↓

Food -Chef -Supplies -Cook food.

↓

Entertainment -Floats -Bands –Costumes.

↓

Clean Up -Cleanup crew -Sweepers/brooms/trash bags -Clean roads after the parade

- Schedule. The schedule below analysis the activities of the time it takes for the project to be finalized and for a successful event to be carried out.

| Task/Activity | Duration | Start Date | Finish Date | Milestone? Y/N |
| --- | --- | --- | --- | --- |
| Project Proposal | 1 week | 5/1/04 | 19/01/04 | N |
| Approval of the Project | 1 week | 20/01/04 | 22/01/04 | N |
| Assigning Project Management Team | 1 week | 23/01/04 | 29/01/04 | Y |
| Survey of the Venue | 1 week | 30/01/04 | 1/02/04 | N |
| Budget Planning | 2 weeks | 02/02/04 | 15/02/04 | Y |
| Raising Fund | 2 weeks | 16/02/04 | 29/02/04 | Y |
| Project Planning | 4 weeks | 1/03/04 | 23/03/04 | Y |
| Planning and collection of resources | 3 weeks | 24/03/04 | 19/04/04 | Y |
| Advertisement | 4 weeks | 20/04/04 | 27/05/04 | N |
| Project Execution | 1 weeks | 28/05/04 | 05/06/04 | Y |

References.

Regni, L. G. J. Class of 2009.

Laine, D., Laine, B., & Peterson, E. (2003). Frommer's Denver, Boulder, and Colorado Springs (Vol. 174).

Ca. Blake, K. S. (2002). Colorado fourteeners and the nature of place identity. Geographical Review, 92(2), 155-179.pstone.

Beckius, J. (2002). North Platte: City between Two Rivers. Arcadia Publishing.