- In pairs, develop a Network Diagram with the provided information

■Use the Critical Path Method to determine the critical path of the project

■Identify each activity, the duration, ES, EF, LS, LF, TF and FF

■Highlight the critical path on the diagram and identify the total duration of the project

| Task | Predecessor(s) | Duration (days) |
| --- | --- | --- |
| A | - | 1 |
| B | A | 3 |
| C | B | 10 |
| D | C | 6 |
| E | C | 8 |
| F | E | 12 |
| G | E,F | 4 |
| H | D,G | 7 |