Critical path

Author

Institutional Affiliation

Course

Instructor

Due Date

Critical path

Question 1: Solution

The project forward pass and backward pass should be used to determine the project duration. The duration of the project is 14 days/weeks. The slack of the activities is calculated by finding the difference between late and early state. The following are the slack for the various activities

A-0

B-0

C-2

D-0

E-0

The critical path is ABDE which is the longest path which includes the activities that have zero slack.

| 6 | C | 3 |
| --- | --- | --- |
| (SL=2) |  |  |
| 8 | 3 | 11 |

| 0 | A | 2 |
| --- | --- | --- |
| (SL=0) |  |  |
| 0 | 2 | 2 |

| 2 | B | 6 |
| --- | --- | --- |
| (SL=0 |  |  |
| 2 | 4 | 6 |

| 11 | E | 14 |
| --- | --- | --- |
| SL=0 |  |  |
| 11 | 3 | 14 |

| 6 | D | 11 |
| --- | --- | --- |
| (SL=0) |  |  |
| 6 | 5 | 11 |

LEGEND

| ES | ID | EF |
| --- | --- | --- |
| Slack |  |  |
| LS | DUR | LF |

Question 2: solution

| 2 | B | 5 |
| --- | --- | --- |
| 25 | Order std. parts |  |
| 27 | 3 | 30 |

| 30 | G | 40 |
| --- | --- | --- |
| 0 | Assemble |  |
| 30 | 10 | 40 |

| 2 | C | 10 |
| --- | --- | --- |
| 3 | produce std. parts |  |
| 5 | 10 | 15 |

| 15 | F | 30 |
| --- | --- | --- |
| 0 | Mfg. custom Hardware |  |
| 15 | 15 | 30 |

| 2 | D | 15 |
| --- | --- | --- |
| 0 | Design custom parts |  |
| 2 | 13 | 15 |

| 40 | H | 45 |
| --- | --- | --- |
| 0 | Test |  |
| 40 | 5 | 45 |

| 0 | A | 2 |
| --- | --- | --- |
| 0 | Order reviewed |  |
| 0 | 2 | 2 |

| 2 | E | 20 |
| --- | --- | --- |
| 20 | software development |  |
| 22 | 18 | 40 |

Critical path is ADFGH

| ES | ID | EF |
| --- | --- | --- |
| SL | DESCRIPTION |  |
| LS | DURATION | LF |

Legend