DOG BOARDING PROJECT TIMELINE, BUBGET AND RESOURCES

Student’s Name

Instructor’s Name

Institution’s Affiliation

Course

Date

Section one-Project time line.

This is a visual list of tasks or activities arranged in a chronological manner for the project managers to view the entirely of the project at one place.

| Task NO. | Task Name | Planned start time | Planned finish time | Duration |
| --- | --- | --- | --- | --- |
|  | Sourcing funds | 15/10/2021 | 25/10/2021 | 10days |
|  | Buying/Renting land | 26/10/2021 | 31/10/2021 | 6days |
|  | Contracts | 5/11/2021 | 10/11/2021 | 10days |
|  | Proposals | 5/11/2021 | 5/11/2021 | 4day |
|  | Document Review | 6/11/2021 | 9/11/2021 | 4days |
|  | Bid Date | 10/11/2021 | 10/11/2021 | 2day |
|  | Award Date | 10/11/2021 | 10/11/2021 | 0days |
|  | Design | 11/11/2021 | 19/11/2021 | 10days |
|  | Apply for permit | 11/11/2021 | 13/11/2021 | 4days |
|  | Start design work | 14/11/2021 | 15/11/2021 | 2days |
|  | Complete design work | 16/11/2021 | 17/11/2021 | 2day |
|  | Point of sale system | 18/11/2021 | 19/11/2021 | 2days |
|  | Procurement | 20/11/2021 | 3/12/2021 | 14days |
|  | Order equipment | 20/11/2021 | 24/11/2021 | 4days |
|  | Order material | 25/11/2021 | 27/11/2021 | 4days |
|  | Hire machines | 28/11/2021 | 3/12/2021 | 6days |
|  | Construction | 4/12/2021 | 4/2/2022 | 62days |
|  | Building kennel | 4/12/2021 | 4/1/2021 | 32days |
|  | Finishing of kennels | 5/1/2021 | 18/1/2021 | 14days |
|  | Play grounds | 17/1/2021 | 23/1/2021 | 8days |
|  | Swimming pool | 24/1/2021 | 4/2/2021 | 10days |
|  | Handing over | 5/2/2021 | 5/2/2021 | 0days |

GANTT CHART

| NO. | Task name | DURATION (DAYS) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 |
|  | Sourcing funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Buying/Renting land |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Contracts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Proposals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Document Review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Bid Date |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Award Date |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Apply for permit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Start design work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Complete design work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Point of sale system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Procurement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Order equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Order material |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Hire machines |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Building kennel |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Finishing of kennels |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Play grounds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Swimming pool |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Handing over |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Section two budget

Project budget

| NO. | Activity | quantity | Budget cost |
| --- | --- | --- | --- |
|  | Buying of Land | 5000sq m | $ 30,000 |
|  | Building kennel | 1000 | $ 10,000 |
|  | Buying resources |  | $5,000 |
|  | Labor |  | $ 5,000 |
|  | Construction of playground |  | $9,000 |
|  | Buying resources |  | $5,000 |
|  | labor |  | $4,000 |
|  | Permit cost |  | $75 |
|  | Point-of sale |  | $1000 |
|  | Total cost |  | $ 50,075 |

Section three resources

Project resources

| RESOURCE NO | RESOURCE NAME |
| --- | --- |
|  | Kennel resources/equipment |
|  | Powder-coated steel |
|  | Galvanized steel |
|  | Stainless steel |
|  | Aluminum |
|  | Bed sheets and mattresses |
|  | Dog beds |
|  | Web camera and screen |
|  | Playing ground resources/equipment |
|  | Dog park benches |
|  | Dog outdoor drinking fountain |
|  | Dog park agility kits |
|  | Dog tunnel |
|  | Dog park shade structure |
|  | Dog park picnic tables |
|  | Dog swimming pool |
|  | Towels |
|  | Refrigerator for medicine and food |
|  | First aid kits for human and dogs. |
|  | Leashes |
|  | Waste bags |