## Main Page
Group Risky 5
PMAN 637 9040
Due 3/16/2021

## Sheet1
Final Project Topic: Risks Associated with Rebulding a Clinic After an Earthquake (Due March 16)
Risk ID# | Identified Scheduling Risk | Mitigating Tasks | Devin's Estimate (hours) | Marizel's Estimate (hours) | Muhammad's Estimate (hours) | Meghan's Estimate (hours) | Dion's Estimate (hours) | Average Estimate (hours) | * Hours based on 8 hour workdays
0.001 | Shortage of Skilled Labor | Immediate advertisement of vacancies both in print and Online Platforms | 18 | 22 | 19 | 16 | 22 | 19.4
|  | Poaching of Skilled workers from other hospitals | 6 | 5 | 5 | 20 | 22 | 11.6
|  | Increase number of hours to work and ensure rotational mechanism is effective | 3 | 6 | 7 | 5 | 3.5 | 4.9
|  | Cross train all volunteers | 40 | 48 | 40 | 40 | 50 | 43.6
Promote from within and carry out on job training
0.002 | Fequently Disruption of Electricity | Ensure Backup Generator is corrrectly working | 3 | 2 | 6 | 6 | 5 | 4.4
|  | Installation of solar pannels to act as backup | 4 | 4 | 4 | 4 | 3 | 3.8
|  | Acquisition of power saving appliances | 9 | s | 10 | 9 | 28 | 14
|  | Repair Installation and upgrade of transmission facilities | 95 | 80 | 90 | 70 | 90 | 85
0.003 | The “Grapevine Effect” | Hold Weekly Project Meetings where information is shared | 3 | 2 | 2.5 | 2 | 3.5 | 2.6
|  | Setting up and ensuring the allowed medium of communication is effective | 4 | 6 | 5 | 3 | 4 | 4.4
|  | Procuring/setting up project-related phones and other communication devices | 10 | 10 | 16 | 17 | 20 | 14.6
|  | Establishing clear communication channels | 8 | 8 | 4 | 16 | 16 | 10.4
|  |  | 8 | 24 | 32 | 16 | 24 | 20.8
0.004 | Injuriies during construction | Ensuring workers sign agreements which takes injuries liability from the hospital | 8 | 24 | 24 | 16 | 24 | 19.2
|  | Procuring and posting Saftey/Hazard signs around the site | 4 | 48 | 60 | 16 | 16 | 28.8
|  | Establish seveal locations for first aid | 8 | 8 | 16 | 8 | 8 | 9.6
|  | Establish fire exiting points and fire assembly | 8 | 8 | 7 | 8 | 8 | 7.8
0.005 | Construction delays | Ensure due deligence thrrought vetting has been effectively done in selecting a contractors | 17 | 16 | 15 | 16.5 | 38 | 20.5
|  | Giving the selected contractors a well efined time frames and schedules | 5 | 9 | 7 | 9 | 26 | 11.2
|  | Promptly paying the contractor to avoid unnecessary delays | 4 | 5 | 4 | 6 | 32 | 10.2
|  | Engage project team* validating tasks and updating the team with any changes introduced. | 5 | 3 | 6 | 4 | 3 | 4.2