ID                        Task

Mode

Task Name                                                     Duration         Start                     Finish                   Predecessors        Resource Names

'20                 Apr 5, '20

S        W        S         T

1                                      1.0 Evaluate User& System

Requirements

10 days         Thu 4/2/20      Wed 4/15/20

4                                           1.2 Configure exchange servers    3 days           Tue 4/7/20      Thu 4/9/20

6	1.2.2  C reate test user accounts in active directory

8                                      2.0 Evaluate ODHS Network

Sustainability

4 days           Fri 4/10/20      Wed 4/15/20

22 days         Thu 4/16/20   Fri 5/15/20

9                                           2.1 Create installation package     10 days         Thu 4/16/20   Wed 4/29/20

12                                               2.1.1 Install work station            3 days           Thu 4/16/20    Mon 4/20/20

13	2.1.2 Create W2K policy for installation

14	2.1.3 Create W2K policy for different users

15	2.2 Test and perfect each policy installation

3 days           Tue 4/21/20    Thu 4/23/20    12

4 days           Fri 4/24/20      Wed 4/29/20  13

12 days         Thu 4/30/20   Fri 5/15/20

16                                               2.2.1 Create CD image                 8 days           Thu 4/30/20    Mon 5/11/20

17                                               2.2.2 Test CD image                     4 days           Tue 5/12/20    Fri 5/15/20      16

18                                     3.0 Conduct E-mail System

Selection

29	3.1.1 Create class workbook for training

22 days         Mon 5/18/20  Tue 6/16/20

10 days         Mon 5/18/20  Fri 5/29/20

Project: Email Upgrade Project

Date: Tue 6/2/20

Task Split Milestone Summary

Project Summary

External Tasks

External Milestone Inactive Task Inactive Milestone Inactive Summary Manual Task

Duration-only

Manual Summary Rollup

Manual Summary

Start-only Finish-only Deadline

Progress

Page 1

ID                        Task

Mode

Task Name                                                     Duration         Start                     Finish                   Predecessors        Resource Names

'20                 Apr 5, '20

S        W        S         T

30                                          3.1.2  Host pilot user training

class

33	4.0 Upgrade ODHS Network & Hardware

12 days         Tue 6/2/20      Wed 6/17/20

10 days         Thu 6/18/20   Wed 7/1/20

35                                          4.2 Finalize and test images            5 days           Thu 6/18/20    Wed 6/24/20

36                                          4.1 Feedback from pilot users        5 days           Thu 6/25/20    Wed 7/1/20    35

37                                     5.0  Develop E-mail Training                15 days         Thu 7/2/20      Wed 7/22/20

38                                     6.0 Deploy email system                      10 days         Thu 7/23/20    Wed 8/5/20    37

Project: Email Upgrade Project

Date: Tue 6/2/20

Task Split Milestone Summary

Project Summary

External Tasks

External Milestone Inactive Task Inactive Milestone Inactive Summary Manual Task

Duration-only

Manual Summary Rollup

Manual Summary

Start-only Finish-only Deadline

Progress

Page 2

Apr 19, '20                  May 3, '20                  May 17, '20                May 31, '20                Jun 14, '20                  Jun 28, '20                  Jul 12, '20                   Jul 26, '20                   Au

M        F         T        S        W        S         T        M        F        T         S        W        S        T        M        F        T         S        W        S        T        M        F         T        S        W        S         T        M        F

Project: Email Upgrade Project

Date: Tue 6/2/20

Task Split Milestone Summary

Project Summary

External Tasks

External Milestone Inactive Task Inactive Milestone Inactive Summary Manual Task

Duration-only

Manual Summary Rollup

Manual Summary

Start-only Finish-only Deadline

Progress

Page 3

Apr 19, '20                  May 3, '20                  May 17, '20                May 31, '20                Jun 14, '20                  Jun 28, '20                  Jul 12, '20                   Jul 26, '20                   Au

M        F         T        S        W        S         T        M        F        T         S        W        S        T        M        F        T         S        W        S        T        M        F         T        S        W        S         T        M        F

Project: Email Upgrade Project

Date: Tue 6/2/20

Task Split Milestone Summary

Project Summary

External Tasks

External Milestone Inactive Task Inactive Milestone Inactive Summary Manual Task

Duration-only

Manual Summary Rollup

Manual Summary

Start-only Finish-only Deadline

Progress

Page 4