ID                        Task
Mode

Task Name                                                     Duration         Start                     Finish                   Predecessors        Resource Names

'20                 Apr 5, '20
S        W        S         T
1                                      1.0 Evaluate User& System
Requirements

10 days         Thu 4/2/20      Wed 4/15/20
4                                           1.2 Configure exchange servers    3 days           Tue 4/7/20      Thu 4/9/20

6	1.2.2  C reate test user accounts in active directory
8                                      2.0 Evaluate ODHS Network
Sustainability

4 days           Fri 4/10/20      Wed 4/15/20

22 days         Thu 4/16/20   Fri 5/15/20
9                                           2.1 Create installation package     10 days         Thu 4/16/20   Wed 4/29/20

12                                               2.1.1 Install work station            3 days           Thu 4/16/20    Mon 4/20/20

13	2.1.2 Create W2K policy for installation
14	2.1.3 Create W2K policy for different users
15	2.2 Test and perfect each policy installation

3 days           Tue 4/21/20    Thu 4/23/20    12

4 days           Fri 4/24/20      Wed 4/29/20  13

12 days         Thu 4/30/20   Fri 5/15/20
16                                               2.2.1 Create CD image                 8 days           Thu 4/30/20    Mon 5/11/20

17                                               2.2.2 Test CD image                     4 days           Tue 5/12/20    Fri 5/15/20      16

18                                     3.0 Conduct E-mail System
Selection
29	3.1.1 Create class workbook for training

22 days         Mon 5/18/20  Tue 6/16/20

10 days         Mon 5/18/20  Fri 5/29/20
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ID                        Task
Mode

Task Name                                                     Duration         Start                     Finish                   Predecessors        Resource Names

'20                 Apr 5, '20
S        W        S         T
30                                          3.1.2  Host pilot user training
class
33	4.0 Upgrade ODHS Network & Hardware

12 days         Tue 6/2/20      Wed 6/17/20

10 days         Thu 6/18/20   Wed 7/1/20
35                                          4.2 Finalize and test images            5 days           Thu 6/18/20    Wed 6/24/20

36                                          4.1 Feedback from pilot users        5 days           Thu 6/25/20    Wed 7/1/20    35

37                                     5.0  Develop E-mail Training                15 days         Thu 7/2/20      Wed 7/22/20

38                                     6.0 Deploy email system                      10 days         Thu 7/23/20    Wed 8/5/20    37
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