The Project Lifecycle

Date: xx January 2018	Time: xxxxxxxx

Answer THREE of the FOUR questions.

If more than three questions are answered, the best three marks will be counted.

Division of marks:  All questions carry equal marks.

BEGIN EACH QUESTION ON A FRESH PAGE

Number of answer books to be provided:  ONE

Calculators permitted:  Casio FX-83/85 MS/ES/GT+ ONLY

Dictionaries permitted:  None

Additional materials:  None

Can question paper be removed from the examination room:  No

Question 1

This question relates to the project lifecycle.

- The figure shown below (F1) represents the processes required to deliver a project into operation. Provide answers to the following questions:

- Give a brief description (50 words) of each of the processes in the ‘product development’ stream.							[3 marks]

- What is the relationship between the processes in the ‘product development’ stream and the processes in the ‘project delivery’ stream?		[2 marks]

- Which processes relate to risk management?				[2 marks]

- Describe a planning process which integrates both process streams.	[5 marks]

F1 – Project Lifecycle processes

- Describe the rework cycle together with its impact on project progress.	[3 marks]

- What is meant by the ‘right hand’ and ‘left hand’ planning rule, and give an example to illustrate your answer?							[3 marks]

- Provide a definition of an integrated project team.				[2 marks]

Question 2

This question relates to High Reliability Organisation (HROs)

- Define an HRO and provide an example of an HRO?			[5 marks]

- Provide a brief description of the following parameters for an organisation to become an HRO, you may wish to use business or operational examples to provide amplification or emphasis:

- Preoccupation with Failure.

- Reluctance to Simplify Interpretations.

- Sensitivity to Operations.

- Commitment to Resilience.

- Deference to Expertise.						[10 marks]

- Briefly discuss the conflict between shareholder value and establishing/maintaining an HRO.										[5 marks]

Question 3

Senior management intend to shorten an important business project by 4 weeks and have asked you to advise the cost of the reduction. The following network (N3) provides details of a project, and the associated cost trade off data for each activity is provided in table (T3).

Project Network N3

Cost Trade-off Data T3

- Study the project network N3 and identify the paths through the network together with the length of each path in weeks.			[5 marks]

- Using this data identify the least cost strategy for reducing the project by 4 weeks.									[15 marks]

Question 4

This question concerns CPM/PERT analysis for a ‘normalised’ project. The activities (in weeks) are detailed in Table T4.

| Activity | Build logic | Pessimistic Time (weeks) | Medium Time (weeks) | Optimistic Time (weeks) |
| --- | --- | --- | --- | --- |
| A | -- | 5 | 6 | 7 |
| B | - | 1 | 3 | 5 |
| C | - | 1 | 4 | 7 |
| D | A | 1 | 2 | 3 |
| E | B | 1 | 2 | 9 |
| F | C | 1 | 5 | 9 |
| G | C | 2 | 2 | 8 |
| H | E, F | 4 | 4 | 10 |
| I | D | 2 | 5 | 8 |
| J | H,G | 2 | 2 | 8 |

Table T4

- Draw a CP Network in ‘activity on line’ format    				  [2 marks]

- Calculate ‘Mean Time’ and ‘Variance’ for each activity			  [3 marks]

- Using ‘mean’ durations to calculate ‘earliest start’, ‘earliest finish’, and slack for each activity (show on your network).			 			  [3 marks]

- Identify the ‘critical path’ on your network and calculate the expected completion time.			 		  					  [2 marks]

- What is the probability that this project will be completed on or before 22 weeks (the required tables are attached?							  [4 marks]

- What is the probability of completing the project in 20 weeks?		  [4 marks]

- Why is Monte Carlo simulation better for calculating the probability of completion within a specified period?							  [2 marks]