Project Communication Matrix

| What information | Communication Mode | Frequency | Provider |
| --- | --- | --- | --- |
| Project status reports | E-mail and hardcopy | Bimonthly | Project manager |
| Team status reports | E-mail and hardcopy | Weekly | Team recorder |
| Issue report | Meeting | Anytime when needed | Team recorder |
| Change request | Meeting and hardcopy | As required | Design department |

Work Breakdown Structure

| Project Name | Trailer Inspection | Date | October 17, 2017 |
| --- | --- | --- | --- |
| Project Number | 296 | Document Number | 1 |
| Project Manager | Austin Yurack | Project Owner/Client | Arrow Container |

| Level | Hierarchical Breakdown | Brief Description |
| --- | --- | --- |
| 1. | Project | Trailer Inspection |
| 2. | Major Deliverable | Fully inspect each trailer and inform management which trailers must be repaired immediately or in the near future |
| 3. | Subdeliverables | Trailer count |
| 4. | Lowest subdeliverables | Location of trailers |
| 5. | Cost Account |  |
| 5. | Work Package | Inspect trailers |
| 5. | Work Package | Inspect trailers within 10 days |
| 5. | Work Package | Cost of project is zero; cost to fix trailers will be found |
| 5. | Work Package | Need quality team |
| 5. | Work Package | Project manager responsible for units of work |
| 5. | Work Package | Measure amount of trailer inspected per day |

| Task Name | Description |
| --- | --- |
| Task 1 | Locate all trailers |
| Task 2 | Reach out to customers to empty trailers |
| Task 3 | Assign drivers to pick up trailers |
| Task 4 | Inspect 5 trailers |
| Task 5 | Inspect 5 trailers |
| Task 6 | Inspect 5 trailers |
| Task 7 | Inspect 5 trailers |
| Task 8 | Inspect 5 trailers |
| Task 9 | Inspect 5 trailers |
| Task 10 | Inspect 5 trailers |
| Task 11 | Analyze condition of all trailers inspected |
| Task 12 | Report findings and provide recommendations on repairs |

| Task Name | Start | End | Duration (days) |
| --- | --- | --- | --- |
| Task 1 | 1/16/2015 | 1/21/2015 | 5 |
| Task 2 | 1/17/2015 | 1/23/2015 | 6 |
| Task 3 | 1/18/2015 | 1/24/2015 | 6 |
| Task 4 | 1/19/2015 | 1/20/2015 | 1 |
| Task 5 | 1/20/2015 | 1/21/2015 | 1 |
| Task 6 | 1/21/2015 | 1/22/2015 | 1 |
| Task 7 | 1/22/2015 | 1/23/2015 | 1 |
| Task 8 | 1/23/2015 | 1/24/2015 | 1 |
| Task 9 | 1/24/2015 | 1/25/2015 | 1 |
| Task 10 | 1/25/2015 | 1/26/2015 | 1 |
| Task 11 | 1/26/2015 | 1/27/2015 | 1 |
| Task 12 | 1/27/2015 | 1/28/2015 | 1 |

Project Schedule

Project Risk and Opportunity Matrix

1=very low 2=low 3=moderate 4=High 5=Very high

| Risk Event | Likelihood | Impact | Detection Difficulty | When |
| --- | --- | --- | --- | --- |
| Failure to locate all trailers | 3 | 5 | 3 | Start-up |
| Miss timeline to inspect trailers | 4 | 5 | 2 | Conversion |
| Trailers not being emptied on time at customer | 3 | 5 | 1 | Start-up |
| Incorrectly inspect/diagnosis trailer | 3 | 5 | 4 | Finalizing |

Risk Management Plan

| ID | Risk | Probability % | Impact (1-5) | Priority | Mitigation Response |
| --- | --- | --- | --- | --- | --- |
| 1 | Fail to locate all trailers | 60% | 4 | 1 | Fully account all trailers, use GPS to track each trailer’s location |
| 2 | Incorrectly diagnosis trailer repair | 50% | 5 | 2 | Use a 100% inspection process |
| 3 | Miss timeline to inspect all traielrs | 50% | 5 | 3 | Set goals on how many trailers per day to inspect |