## Sheet1
WBS ID | TASK LEVEL | TASK NAME | RISK DESCRIPTION | RISK CATEGORY | RISK PROBABILITY | INITIAL RISK SCORE | RISK CONSEQUENCE | RISK HANDLING CATEGORY | RISK CONTROL PLAN | RISK OWNER | MITIGATION COST | Remaining Probability After Mitigation | Overall Risk Impact
1 | 1 | Complete Phase One
1.1 | 2 | Meet with stakeholders
1.1.1 | 3 | Create Project Requirements
1.1.1.1 | 4 | Aquire current employee information | No suitable candidate found | People | 15% | 100000 | Project canceled | Reduction | Reach out to prospective PM's at least one month in advance | HR Manager | 3000 | 5% | High
1.1.1.4 | 4 | Establish budget | project funding approval delayed | Financial | 5% | 1000 | Project start delayed | Accept | Clearly defined deadlines, open communication, | Project Manager | 0 | 1% | Low
1.1.2.4 | 4 | Generate first draft of charter | Project management team unable to come to an agreement | Political | 30% | 1500 | project scope not clearly defined | Reduction | Careful review of project requirements to include technical and functional requirements for the client | Project Team, Project Manager | 0 | 10% | Low
1.4 | 2 | Set up internet service
1.4.1.2 | 4 | Receive quotes from providers | delay receiving quotes | External | 20% | 5000 | schedule delayed | Reduction | Follow up on quotes to ensure they are delivered on schedule | Purchasing Manager | 0 | 10% | High
1.4.1.4 | 4 | Set appointment with chosen provider | scheduling conflict with client and field technician | Schedule | 10% | 2500 | schedule delayed | Sharing | Schedule survey afterhours, over multiple days. | Field Technician | 1500 | 5% | Low
1.4.1.5 | 4 | Review service provider contract with stakeholder | Review reveals additional work to be done | Technical | 45% | 2000 | Scope adjusted, schedule delayed, expenses increase | Sharing | Issues will need to be addressed in order to complete the project | Project Manager, Field Technician | 1000 | 25% | Low
1.4.1.6 | 4 | Sign contract with provider and stakeholders | Only one service provider in the area | External | 30% | 2500 | 2500 | Accept | Sign contract with service provider | Purchasing Manager | 2500 | 30% | Low
1.4.2.1 | 4 | Receive Network Equipment Delivery from ISP | delivery delayed due to inclement weather | weather | 35% | 0 | schedule delayed | Accept | Wait for the order to arrive | Field Technician | 0 | 35% | High
1.4.2.1.1 | 5 | Order Printers | printer cost higher than expected | Financial | 20% | 1500 | 4000 | Accept | Purchase the needed printers | Purchasing Manager | 1500 | 10% | Low
1.4.2.1.2 | 5 | Order Network Services | order placed incorrectly | Technical | 25% | 2000 | expenses increased, schedule delayed | Sharing | Double check order with ISP recommendations for equipment before the order is oficially placed | Purchasing Manager | 0 | 5% | High
1.4.2.2 | 4 | Set up central modem | ISP technician does not show | External | 25% | 1000 | schedule delayed | Transfer | Remain in contact with ISP to ensure appointment will still happen as scheduled | Field Technician | 0 | 10% | Medium
1.4.2.6 | 4 | Additional Network system and devices
1.4.2.6.2 | 5 | Setup local data backup device | physical configuration offers limited functionality for all business practices | Enviornmental | 30% | 0 | schedule delayed | Accept | Figure out a new way to rearrange equipment to suit the needs of the business | Field Technician | 0 | 30% | Medium
1.4.2.6.4 | 5 | Install shared network printers | client wants additional printers | Client | 40% | 500 | 500 | Reduction, Accept | Clarify with the client the need for the additional equipment and if it is justified order the additional equipment | Field Technician, Purchasing Manager, Client | 500 | 40% | Medium
Total | [10 empty] | 10000