Project Charter

Cafe Millennium

Projecting Prosperity

March 13, 2020

PMAN 634, Section 9080, Spring 2020

Christina Barnett

Gwendolyn Boyd

Elizabeth Boyer

Marizel Brewington

# Document Change History

| Date changed | Change details | Reason for change (if applicable) | Responsible for change |
| --- | --- | --- | --- |
| March 7, 2020 | Initial draft | Document Initiation | E. Boyer |
| March 10, 2020 | Portion of project launch, scope, objectives, role description, and overall project risk | Missing content in section completed | M. Brewington |
| March 10, 2020 | Purpose for the project, project manager and authority level, and criteria for project approval | Missing content in section completed | E. Boyer |
| March 12, 2020 | Project objectives, review of content | Missing content in sections completed | G. Boyd |
| March 12, 2020 | Multiple sections updated and revised transitions | Missing content in sections completed | C. Barnett |
| March 12, 2020 | Collaborative review and document expansion | Expand project charter and add supporting documentation | All members |
| March 13, 2020 | Final review and editing by all team members | Document finalized | All members |

# Table of Contents

Document Change History	2

Table of Contents	3

Cafe Millennium Launch	4

Purpose for the Project	4

Project Scope Statement	5

Project Objectives and Success Criteria	6

Objectives	6

Project Requirements	7

Milestone Schedule	8

Budget or Pre-approved Financial Resources	10

Criteria for Project Approval	11

Project Authority	11

Project Manager and Authority Level	12

Other Project Roles and Authority Level	12

Project Sponsor or Customer and Authority Level	13

References	14

# Cafe Millennium Launch

Cafe Millennium has won the bid for the launching of their small business. In the weeks to come, Projecting Prosperity will execute this project charter and establish a modern Cafe that will cater to the growing number of young professionals in the immediate area. With this idea, the launching of this cafe is likely to disrupt the business in the region. Previously, a cafe was vastly known for offering light meals and drinks. The launch of Cafe Millennium will evolve and expand services to include free gigabit speed internet access, collaborative working areas, and cafe hosted networking events that will aim to cater towards younger generations. The project management firm, Projecting Prosperity is vested in the success of Cafe Millennium to ensure financial payment for services and to earn positive ratings for the professional portfolio.

# Purpose for the Project

Projecting Prosperity is promoting the Cafe Millennium launch to capitalize on high return of investment and to help fulfill a community need that is lacking. Currently, the business park has no modern cafe or meeting space within a reasonable driving or walking distance; an establishment can easily be integrated. Today’s restaurant chains are connecting more with their customers in a way that gives insight into the restaurant. Social media marketing and community engagement have been shown to yield greater competitive advantages (Kim, Yoo, & Yang, 2020). Food enthusiasts are not just interested in what is on the menu, they want a sense of connection with a business and one that supports their lifestyle. Cafe Millennium will be in a newly developed business park where young professionals and food enthusiasts can gather to enjoy small bites and drinks in a relaxing environment. There is a noticeable disconnect in the community; the cafe will foster in-person collaboration and networking between young professionals, while also promoting community engagement. The establishment of Cafe Millennium will lead to the creation of well-suited job opportunities for students and locals, aiming to engage employees in all aspects of the business. The cafe plans to collaborate with colleges in the area to offer internships for students interested in entrepreneurship and marketing. Moreover, the Cafe will partner with established companies in the business park to host regular networking events and job fairs. Cafe Millennium will be an integral part of the community.

# Project Scope Statement

Cafe Millennium aims to provide excellent coffee and food service to a newly established business park, while creating a sense of community amongst its patrons and providing a space for young business professionals to gather and network. Over the first ninety days the final project funding must be secured through a small business loan and a budget finalized. Next the business can enter the phase of locating and leasing a space, complete all related build out and business purchasing, and hire staff. All of this culminates in the marketing and grand opening of the Cafe.

The firm must abide by non-negotiable boundaries set by the customer.  The first requirement is that the cafe's location should be confined to the business park, placing it less than one miles walking distance from all the major business companies leasing a space in the park. The next required limit is to keep the project under the $75,000 budget. This is the maximum guaranteed funding that exists when combining projected loan amounts and personal investment from the customer. Last, there are also constraints on the order in which phases may occur. Many of the phases are dependent on the prior phase being complete and could be considered a waterfall model. The project will be conducted in five phases:

- Secure loans and vendor contracts

- Locate a space and begin design plan

- Secure required permits

- Marketing and sales

- Opening to the public

# Project Objectives and Success Criteria

Project success is multi-faceted and can be measured within the triple constraint (time, quality and budget) and it can also include criteria such as customer and stakeholder satisfaction. Success criteria are by their nature highly dependent on the circumstances for the individual project; it is advisable to base all success criteria on the results of the stakeholder analysis and to ensure that each of the criteria is measurable (O'Brochta, 2002). The Projecting Prosperity firm has identified measurable objectives and will determine overall project success by the accomplishment of set predetermined objectives.

## Objectives

- Ensure that adequate funds for running the project has been sourced within the first three months before the project initiation

- Ensure that qualified employees are recruited within 30 days before the project initiation

- Present the sales and marketing plan to the management for implementation one week after the completion of the recruitment exercise

- Ensure all project officers are in operation within the first year

- Secure funding in 60 days

- Hire employees

- Present sales and marketing plan, action plan or marketing strategies

- Target opening in one year

- Establish a reward program to ensure repeat customers; surprise customers with a freebie from the menu after several visits

- Offer a variety of healthy food items on the menu to appeal to various diets including, vegetarian, vegan, organic, plant-based, non-GMO

- Limit food waste to no more than five percent of total sales

## Project Requirements

Requirements fulfill a double role of first recognizing then, continuously verifying the project's assumptions and constraints (Boyle & Mayes, 2012). Requirements are used to guide the development of deliverables and must be clearly identified. In addition, they provide a means for holding the project management team and stakeholders accountable. Listed below are requirements outlined by the firm on behalf of the Cafe Millennium project:

- Secure building codes/permit from the local county prior to operation

- Secure a business permit and pay any applicable taxes

- Obtain a food service license from the county health department

- Establish an EIN (Employer Identification Number)

- Pass the building inspections and secure a Certificate of Occupancy

- Consult local government officials to aid in compliance with regulatory requirements

- Contact ADP to set up proper security systems

- Technical walkthrough and installation of internet and access points for patrons

- Technical setup of all business-related computers and payment terminals

- Complete project within allocated budget and timeframe

- Comply with the Green Building Act of 2006

- Pay employees above minimum wage ($13) with benefits guaranteed or Comply with the State Minimum Wage and Overtime Law

- Conduct the project in five phases

Overall Project Risks

All projects have some associated risk so, it is important to be able to find a balance between risks and rewards that works in favor of the success of the project; risk management identifies and manages risk in a controlled manner (Project Management Institute, 2017).

- Since the idea in this project is new, there is a high risk that the business will fail in various areas during the first five years.

- Making a budget for this type of a project is time consuming because it involves various deliverables.

- Fire outbreaks are very common in cafes since a lot of cooking is involved. When this happens, huge losses can occur.

- With business booming in this region, many similar projects are likely to be initiated, leading to stiff competition.

- Meeting salary demands of some of the experienced employees is going to be a problem given that this is just a startup business.

## Milestone Schedule

| Phase | Goal(s) | Milestones | Deadline |
| --- | --- | --- | --- |
| I | Secure Loans Secure Vendor Contracts | Business loan (60 days) | 60 Days |
|  |  | Food vendor (US foods contract) |  |
|  |  | Daily consumables / housekeeping supplies |  |
|  |  | Hire Waste Management |  |
|  |  | Hire Pest Control |  |
| II | Locate a space Begin design plan | Hire realtor or builder? | 90 days |
|  |  | Lease a space for the business |  |
|  |  | Interior designer |  |
|  |  | Furniture contract (multipurpose furniture) |  |
|  |  | Landscaping company |  |
| III | Secure Permits | Preventative Maintenance contract (regular and emergency repairs) | 30 days |
|  |  | IT company (set up networking and business equipment) |  |
|  |  | Permit to operate in the county and state |  |
|  |  | Inspection and Security/Safety Permit |  |
|  |  | Food Service Permit |  |
| IV | Marketing & Sales | Begin marketing campaign (grand opening notice, coupon offers, etc.) | 60 days |
|  |  | Complete SWOT analysis for competition |  |
|  |  | Create sales goals |  |
|  |  | Sales blitz - with menu or flyers on hand, visit nearby companies and invite them for the Grand Opening. |  |
|  |  | Outreach to community business for partnership |  |
| V | Grand Opening | Grand opening preparation | 2 weeks |
|  |  | Ribbon cutting ceremony with the Chamber of Commerce |  |
|  |  | Serve the first customers |  |

## Budget or Pre-approved Financial Resources

The Cafe is being financed through two different sources. First, the local business owner and entrepreneur will be investing their own personal funds. In addition, a small business loan will be taken out to cover additional costs. Together, the funding sources total $75,000. This budget will be taken into consideration by the firm during all planning and execution phases.

Budget

| Human resources |  |
| --- | --- |
| Payroll expenses | $6,000 |
| Staff | $4,000 |
| Training | $2,000 |
| Equipment |  |
| Computers | $7,000 |
| Office equipment | $7,000 |
| Kitchen equipment | $3,000 |
| Maintenance of equipment | $2,000 |
| Consumable materials |  |
| Housekeeping | $8,000 |
| Daily supplies | $5,000 |
| Food | $10,000 |
| Bills |  |
| Lease | $6,000 |
| Utilities | $15,000 |
| TOTAL | $75,000 |

## Criteria for Project Approval

It is essential that Cafe Millennium meets all project requirements. Project management will determine success based on maintaining deadlines set and sticking to the project timeline. When all the phases of the project are finished, the local investor, owner, and project manager will finalize the project. The owner will have the final approval for the opening of the business. For progress monitoring purposes, the number of customers will be documented, and customer feedback surveys will be analyzed. Overall, the lender will determine success of the project based on loan payback.

# Project Authority

An appropriate and controlled authority level is important for a successful project; it is dynamic, evolving over the course of the project (Stickney & Johnston, 1983). Projecting Prosperity will be the operating authority for the project itself, which includes the authority to acquire vendor services and the authority to aid in decision making processes. The customer also plays a vital role. The project is under review by the customer, since they are stakeholders of the project. Customers will have the authority to demand changes.

## Project Manager and Authority Level

Project management is essential to the accomplishment of projects. Project managers can use prior knowledge and project management tools to execute project requirements successfully (Project Management Institute, 2017). Elizabeth Boyer, an experienced employee of Projecting Prosperity has been selected as the Project Manager. She will be responsible for the coordination of daily duties. She will be the point of contact for any questions regarding the project. Elizabeth will mitigate risks and solve problems regarding aspects of the launch and progress of Cafe Millennium. She will be an active force throughout all stages of the project. She will conduct biweekly meetings to ensure collaborative effort across the board.

## Other Project Roles and Authority Level

In addition to the project manager, a variety of key roles and responsibilities will need to be filled to successfully operate the Cafe. A Marketing and Sales Management team will be responsible for implementing marketing and sales plans based on demand segments to maximize revenue. They will identify why competitors are successful in each demand segment and directly market and sell against them. Moreover, they coordinate advertising, public relations, and promotional programs. A Profit Manager will plan to meet or exceed budgeted profit margin for the cafe and prepare an annual budget that reflects the business plan. The profit manager will ensure staff are trained in financial control procedures for cash, vouchers, inventories and receivables. The role of Human Resource Manager will maintain a positive and cooperative work environment between staff and management. They are responsible for resolving grievances, administering policies, and monitoring and maintaining acceptable turnover levels. Safety and Security Management will understand local health and safety codes and regulations that apply to the business and highlight security procedures that should be adhered to, such as locking the doors and arming the alarm system after hours. An Accountant will be responsible for measuring profits and ROI in addition to taking care of tax documentation.

## Project Sponsor or Customer and Authority Level

The client, Christy Barnett, is an entrepreneur that approached Projecting Prosperity to contract Project Management services for Cafe Millennium. Investing her own funds, in addition to a small business loan, the client is an acting project sponsor. The firm set up an initial meeting with the client to gather high and mid-level requirements and will use the feedback to draft management tools such as the Work Breakdown Structure to highlight deliverables. Acting as a high level of authority, the client will be responsible for signing off after each phase has been completed. This will serve as a checkpoint for the firm and a level of assurance that the client is satisfied with the firm's fulfillment and delivery of the phase. In addition, the PM team will meet with the customer biweekly to review progress and address any concerns. The customer holds the ability to force a change in requirements for the project at any time desired. Any adjustment has the potential to skew the project timeline, so the firm will be responsible for assessing the change request, assigning a level of effort, and informing the client of any perceived effects and consequences, prior to deciding.

The final project charter will include both signatures from the firm's designated project officer and the client. "The signature of a customer at the bottom conveys authority from the customer-side, and the counter-signature of an officer of the consultancy makes the agreement binding on the consultant-side" (Brown, 2005). In addition, a notary will be present to make the document official.

# References

Boyle, M. & Mayes, J. L. (2012). Set in stone. PM Network, 26(12), 20–22.

Brown, A. S. (2005). The charter: selling your project. Paper presented at PMI® Global Congress 2005—North America, Toronto, Ontario, Canada. Newtown Square, PA: Project Management Institute.

Kim, B., Yoo, M., & Yang, W. (2020). Online engagement among restaurant customers: The importance of enhancing flow for social media users. Journal of Hospitality & Tourism Research, 44(2), 252-277.

O'Brochta, M. (2002). Project success—what are the criteria and whose opinion counts? Paper presented at Project Management Institute Annual Seminars & Symposium, San Antonio, TX. Newtown Square, PA: Project Management Institute.

Project Management Institute. (2017). A Guide to the Project Management Body of Knowledge (PMBOK® Guide) — Sixth Edition and Agile Practice Guide (ENGLISH). (pp. 10, 397). Project Management Institute.

Stickney, F. A. & Johnston, W. R. (1983). Delegation and a sharing of authority by the project manager. Project Management Quarterly, 14(1), 42–53.