Finance Assignment

Student Name

University

Course

Professor Name

Date

Part 1

- Precedence table

| Activity number | Task description | Time for activity (weeks) | Total cost (€) | Precedence |
| --- | --- | --- | --- | --- |
| A | Approval | - | - | - |
| B | Build Prototype | 2 | 3200 | A |
| C | Test Prototype | 3 | 4800 | B |
| D | Source-purchase Parts | 2 | 1600 | B |
| E | Final Build | 4 | 6400 | C,D |
| F | Canvass Customers | 6 | 10800 | B |
| G | Final testing | 2 | 5200 | E |
| H | Customer demonstration | 2 | 6800 | F,G |
| I | Completion | - | - | H |

- Critical path

A, B, C, E, G, H, I   the critical path takes (2+3+4+2+2=13 weeks)

- Float time

Float time = Critical path – Second longest sequence of activities

The second longest sequence of activities is A, B, D, E, G, H, I which takes (2+2+4+2+2=12 weeks)

Float time is 13-12=1 week.

d)  Table showing allocation of labor resources and total labor cost

| Activity | Time in weeks | Cost (time × cost of unit) (€) | Totals in (€) |
| --- | --- | --- | --- |
| A | - | - | - |
| B | 2 | 1600 × 2 | 3200 |
| C | 3 | 1600 × 3 | 4800 |
| E | 4 | 1600 × 4 | 8000 |
| G | 2 | (1600 × 2) + (1000×2) | 5200 |
| H | 2 | (2400 × 2) + (1000 × 2) | 6800 |
| I | - | - | - |
| Total | 13 |  | 28800 |

For one week = (28000  ÷ 13) €

=2153.85€

Part 2

a)

| Activity number | Task description | Time for activity (weeks) | Total cost (€) | Precedence |
| --- | --- | --- | --- | --- |
| A | Approval | - | - | - |
| D | Source-purchase parts | 2 | 1600 | A |
| B | Build prototype | 2 | 3200 | A |
| C | Test prototype | 3 | 5400 | B |
| E | Final Build | 2 | 3200 | C,D |
| F | Canvass customers | 6 | 10800 | B |
| G | Final testing | 2 | 5600 | E |
| H | Customer demonstration | 2 | 6800 | F,G |
| I | Completion | - | - | H |

b) Critical path

A, B, F, G, E, H, I critical path takes (2+6+2+2+2=14 weeks)

c) Comment on any changes to float times

Float time = Critical path – Second longest sequence of activities

The second longest sequence of activities is A, B, C, E, H, I which takes (2+3+2+2=9weeks)

Float time is 14-9=5 weeks.

The float time increased by four weeks, meaning that even if the production starts later than the expected time, the deadline for delivery will not be extended.

d) The revised labor cost.

| Activity | Time in weeks | Cost (time × cost of unit) (€) | Totals in (€) |
| --- | --- | --- | --- |
| A | - | - | - |
| B | 2 | 1600 × 2 | 3200 |
| F | 6 | 1800 × 6 | 10800 |
| G | 2 | (1600 × 2) + (1000 × 2) | 6200 |
| E | 2 | (1600 × 4) | 6400 |
| H | 2 | (2400 × 2) + (1000 × 2) | 6800 |
| I | - | - | - |
| Total | 14 |  | 33400 |

For one week = (28000  ÷ 14) €

=2385.71€

Part 3

The critical path method (CPM) illustrates the various activities involved in a project and shows how they relate to each other. While in the past people had to manually draw the CPM, currently we can use computer programs to create the CPM. The time required for project completion can best be shortened if experts can effectively shorten activities along the critical path. Since only one-tenth of the activities in large jobs matter, project managers use the CPM to shorten at least one critical activity so they can shorten the entire project. However, this increases the chances of shifting the critical path to non-critical jobs.

When shortening the critical path (CP) people should consider the economic and engineering issues involved. Practically, project managers can considerably reduce the time it takes to complete critical jobs but they have to identify whether this could be possible through ways such as increasing the number of people working on the project, using better equipment, and working overtime. Using the CPM ensures that people concentrate on jobs that affect project completion time, highlights the impact of shortening activity jobs, and allows users to study issues that can arise with a “crash” program.

When creating a CPM the starting time that a project starts is labeled S while the earliest time that an activity can start is labeled (ES). The earliest finish time (EF) is calculated by summing up the early start (ES) and the time it takes to complete a project (t). Also, the CPM has the latest start and finish times. In this case, we must have the latest target time (T) which must be at least equal to the finish time (F). If this assumption is true, users identify the latest time for finishing the project (FT) without delaying the project beyond (T). The late start time (LS) is arrived at by subtracting the job time (t) from the late finish (LF).

In some instances, some jobs have a late start that equals an early start. The difference between activity early finish and late finish is known as total slack (TS), which simply means the maximum time an activity can be delayed beyond the ES while meeting the deadline for delivery. The practicality of slack is that activities with a positive total slack have an allowance for the start time delay. Project managers can use free slack well at the operating level.

When job data provides enough information about the costs of doing all activities then the calculation of the project will be very easy. When job speed is determined by the size of the team, the project can be lengthened or shortened by adjusting group size. There are potentially many ways of reducing the time taken to do a job, but any attempt to speed up has disadvantages. The CPM is the best method for determining how to undertake a project within the shortest possible time and low cost.

References

Levy, F.K., Thompson, G.L., & Wiest, J .D. (1963). The ABCs of the critical path method. Harvard Business Review, September.