## Sheet1
TASKS | START DATE | DAYS TO COMPLETE
Site selection | 2019-01-02 | 30
Project design | 2019-02-01 | 14
Selecting a contractor | 2019-02-14 | 7
Business plan to obtain finance | 2019-02-20 | 9
Constuction of the site | 2019-03-01 | 106
Playground preparation | 2019-06-14 | 11
Furnishing and Equipping the classrooms | 2019-07-02 | 31
License approval for the facility | 2019-08-01 | 31
Identify the Personnel | 2019-09-01 | 16
Marketing the program to the Community | 2019-09-16 | 15