Action plan for accomplishing smart goals

Name

Instructor

Course

Date

Goal: To achieve production efficiency in my department

| Activities | Responsibility Primary Others | Obstacles/Comments | Start Date | Finish Date |
| --- | --- | --- | --- | --- |
| Conduct an in internal audit of the processes in the department | To identify production gaps in the production process | Lack of required materials or information for the audit. Lack of monetary support for the operation. | October 1, 2019 | November 31, 2019 |
| Conduct a research within the student organization | To get more ideas on how to improve productivity in the department. Involving relevant stakeholders in streamlining the changes. | Lack of corporation from fellow students. Lack of corporation from the school administration. Internal disputes in handling department affairs. | December 1, 2019 | January 1, 2020 |
| Implementation of the necessary changes as per the research findings | Assign duties to all involved members. Establish a control office to oversee the implementation of the recommended changes. | Limited resources as compared to what is recommended for change. | January 1, 2020 | September 1, 2020 |

Goal: To improve executive leadership skills

| Activities | Responsibility Primary Others | Obstacles/Comments | Start Date | Finish Date |
| --- | --- | --- | --- | --- |
| Identify leadership weaknesses within the executive | Try to understand areas where the gaps are and the causes of the gaps. | Lack of leadership mentorship program to help in identifying weaknesses | September 30, 2019 | December 1, 2019 |
| Identifying a strategy for improving leadership skills | Training executives on leadership skills. Organizing workshops on leadership for all members. | Limited resources to undertake respective exercises. Lack of full commitment and goodwill from the executives. | January 1, 2020 | April 30, 2020 |
| Identifying key positions that require much experience | Intensive training on respective leaders on what is required | Lack of corporation from individuals identified. Time factor | May 1, 2020 | September 30, 2020 |