Operational Plan: Template

| Objective: Recruit Dr. Oz to practice at our facility |  |  |  |  |  |  | Outcome: Increase patient volume by 25% within 3 months |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategies: | Projects/Activities: | Time Frame |  |  |  |  |  |  |  |  |  |  |  |  | Person(s) Involved | Budget |  |
|  |  | Q1 |  |  | Q2 |  |  |  | Q3 |  |  | Q4 |  |  |  |  |  |
|  |  | J | F | M | A | M |  | J | J | A | S | O | N | D |  | Needed | Estimated |
| Contact Dr. Oz | 1.Research what talent agency or management company represents Dr. Oz 2. Check licensed specialties of Dr. Oz (find the most beneficial way to implement his presence) 3. Pitch proposed idea and secure his participation | X X X | X |  |  |  |  |  |  |  |  |  |  |  | Project Manager CEO CFO Board of Trustees | Salary for Dr. Oz | $10, 000 per month |
| Set up a meeting to implement contract | 1. Get schedules of key members of the organizational team 2. Include legal counsel (discuss any specifics we need to understand prior to securing a contract with Dr. Oz) |  | X X |  |  |  |  |  |  |  |  |  |  |  | Project Manager Administrative Assistant COO Legal Department | Legal fees | $5,000 to $8,000 |
| Produce marketing materials for the new provider | 1. Purchase commercial ad space 2. Source commercial production companies 3. Design, order, and distribute printed materials |  |  | X X | X | X |  |  |  |  |  |  |  |  | Project Manager Marketing Department External Contractors | TV ads Production costs Material costs | $8,000 $1,500 $2,300 |
| TOTAL MONTHLY COST: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $34,800 |