## Slide 1: Project Management Operations
MSPM1-GC2030
MSPM1-GC2030
Session Number 4
Project Work Plan Part 2: Scheduling

## Slide 2: Agenda
Scheduling
Network Diagram
Estimating Resources
Critical Path
HBS Game Simulation

## Slide 3: Understanding schedule management
MSPM1-GC2030
3
Decompose the scope into a WBS
Determine resource skills
Estimate labor utilization, i.e., hours
Develop a network diagram
Create a Gantt chart
Track plan vs. actual
Measure schedule variances, i.e., SV, SPI

## Slide 4: High-Level Scheduling
MSPM1-GC2030
4
Define Activities
Sequence activities
Estimate Activity Resources
Estimate Activity Durations
Develop Schedule
Control Schedule

## Slide 5: High-Level Scheduling
MSPM1-GC2030
5
Define Activities
Sequence activities
Estimate Activity Resources
Estimate Activity Durations
Develop Schedule
Control Schedule

## Slide 6: What You Need to Define Activities
MSPM1-GC2030
6
Organizational Process Assets
  Lessons learned from prior projects
Enterprise Environmental Factors
  Project management system
  Other factors
WBS

## Slide 7: How to Define Activities
MSPM1-GC2030
7
Prior plans
Decomposing WBS work packages
Expert Counsel
Plan in Phases
  Plan what you know now, leave the rest at milestones

## Slide 8: Define Activities Output
MSPM1-GC2030
8
Activity List
Activity Attributes
Milestone Lists

## Slide 9: Define Activities Output
MSPM1-GC2030
9
Activity List
Activity Attributes
Milestone Lists

## Slide 10: Sequence Activities
MSPM1-GC2030
10
Put the list of activities in order!

## Slide 11: Network Diagram Use a network diagram to visualize the way activities relate.
MSPM1-GC2030
11
www.projectminds.com

## Slide 12: Network Diagram Terminology
MSPM1-GC2030
Project Network Diagram: Any schematic display of the logical relationship between project activities.
Path: A sequential order of activities defined by the project network logic.
Event: When an activity is either completed or started.
Node: a junction point joined to some or all of the other dependency lines (paths).

## Slide 13: Make a Network Diagram!
MSPM1-GC2030
Name | Predecessor
Start | -
A | Start
B | A
C | B
D | Start
E | D
F | B
G | C
H | D
I | E, H
Finish | F, G, I

## Slide 14: Scheduling Terminology
MSPM1-GC2030
Predecessors: Those activities that must be completed before initiation of a later activity in the network.
Successors: Activities that cannot be started until previous activities have been completed. These activities follow predecessor tasks.

## Slide 15: Using Predecessors
MSPM1-GC2030
Finish to Start (FS)
Start to Start (SS)
Finish to Finish (FF)
Project planning software with predecessors
  Can auto update when dates change
  Robust and logical

## Slide 16: Leads and Lags
MSPM1-GC2030
Lead time - when you give a successor task some time to start before the predecessor finishes.
Lag time - when you put a delay between the predecessor task and the successor.

## Slide 17: Estimating Resources
MSPM1-GC2030
Resource Calendars
  Certain people, rooms, and other resources are only available at certain times.
Activity List
Activity Attributes (what will the resources going do?)

## Slide 18: How to Estimate Resources
MSPM1-GC2030
Expert Judgement
Estimating Data
Alternatives Analysis
Project Management Software
Bottom-Up estimating
Parametric estimating

## Slide 19: How to Estimate Activity Durations
MSPM1-GC2030
Expert Judgement
Analogous Estimating
Parametric Estimating (software/formula driven)
Three-Point Estimates
  Realistic
  Optimistic
  Pessimistic
Reserve Analysis
  Also known as ‘contingency’ or ‘buffer’ = Team
  Management Reserve = Financial Controller

## Slide 20: PERT (Project Evaluation Review Technique)
MSPM1-GC2030
(Optimistic Duration + 4(Most Likely Duration) + Pessimistic Duration
6

## Slide 21: Critical Path
MSPM1-GC2030
Every network diagram has a critical path - which is the string of activities taking up the longest duration in the network diagram.
Critical Path is important because it tells you what absolutely has to be completed when. If these events do not finish at the prescribed time in the path, your project will not finish on time.
Project managers constantly monitor their critical path - especially when the project experiences delays.

## Slide 22: Almost Finished: Estimate Activity Durations
MSPM1-GC2030
How long is this going to take us - based on who is available.
  “Jack is on vacation for the month of August, so we can’t allocate the servers needed for the upgrade until he returns.”
  It may only take 1 week to allocate the servers (effort), but the duration will be affected by Jack’s vacation.

## Slide 23: Managing Schedule Variances:
MSPM1-GC2030
Methods to accelerate work -
Fast tracking: Concurrent/ Parallel activities
Crashing: Add a new crew to work; duplicate labor
What are other methods to remediate schedule variance?

## Slide 24: Baseline:
MSPM1-GC2030
Snapshot of the plan as of the start date or revision date
Use the baseline to compare the plan to actual
Plan = The work that was planned to be done
Actual = The work that was actually done

## Slide 25: Suggested Artifacts on YouTube
MSPM1-GC2030
25
Constraints, Baselines and Requirements:
https://www.youtube.com/watch?v=JtNq0AlxT10&list=PLbuA2svvSuTpAIHKqOWIAPabnGE75e1IR
WBS:
https://www.youtube.com/watch?v=SqcuLsyFr-o
Project Scheduling:
https://www.youtube.com/watch?v=Rq19ga0U_jQ
Work Packages:
https://www.youtube.com/watch?v=jh-3c6WBhBE
Monitoring and Controlling:
https://www.youtube.com/watch?v=Bo9lVmeU4MY
Sample Gantt Chart in Excel: Chris Croft
https://www.youtube.com/watch?v=dDetfOCCMQo

## Slide 26: Case Studies in Schedule Management: Today’s reading Lessons Learned: Team Breakouts in-class exercise
MSPM1-GC2030
Team 1: Case 4.1: Material Delays
Team 2: Case 4.2: Union Strike in France
Team 3: Case 4.3: Scheduling Challenge
Team 4: Case 4.4: Different Time Zones
Team 5: Case 4.5: Critical Path Tasks
Team 6: Case 4.6: Estimating Tasks

## Slide 27: Project Management Operations GC2030 Game Simulation:
Harvard business school publishing

## Slide 28: Run Summary– Game Simulation

## Slide 29
Game Simulation:
Update:
Start by accessing the coursepack.
Accessing Course Material (a Coursepack) Assigned to You
PROJECT MANAGEMENT SIMULATION: SCOPE, RESOURCES, SCHEDULE V2
Click: https://hbsp.harvard.edu/import/802277 (Monday)
Click: https://hbsp.harvard.edu/import/802281 (Wednesday)
Play Scenario A
Get Site help at: https://help.hbsp.harvard.edu/hc/en-us
Objective: The learning outcome is the ability to understand the project constraints, adapt inputs to improve the project outcomes, and apply and interpret the EVM measurement framework to assess project performance.
Harvard Business School Publishing

## Slide 30: Run Summary– Game Simulation
The maximum number of points for meeting the targets is 700.
Additional points are awarded for exceeding the target.
Scope
Cost
Team Morale
Schedule
Schedule
Schedule
Harvard Business School Publishing

## Slide 31: Session Recap