Monitoring and Evaluation Plan Template

|  | Outputs |  | Outcomes |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Activities | Participants | Short Term | Mid Term | Long Term |
| Indicator This is what you are going to measure or evaluate. There should be an entry in each column. This should come from your logic model. | Information sessions: target 5 sessions at 4 local high schools | Teens age 14/15 attending 9th grade at Corktown, Central, Hamtramack and Eastern high schools in Wayne County | Knowledge of the physiological and social effects of tobacco use. | Smoking cessation Never started tobacco use | Decrease in pre-term delivery |
| Frequency How frequently will data be collected | Monthly | Monthly | Quarterly | Annual | Annually |
| Data Source What is the source of the data? | Program staff activity report | Sign in sheets | Pre- and post- session tests | Survey Urine screen | County Vital Statistics |
| Data Collection Method How is this data getting into a format that can be analyzed? | Each program staff must submit location and date of sessions in monthly activity report | Program presenters will tally attendance numbers in monthly activity reports | Results from each participant entered into an Access data base for quarterly analysis. | A self-assessment survey to evaluate tobacco Cotinine/nicotine Dipcard test performed by program personnel. Results entered into Access database. | Download from Waynecountly.gov |
| Report To whom will this data be reported | Program coordinator Included in biannual report to Riverdale foundation Included in annual report to Board of Directors | Program coordinator Included in biannual report to Riverdale foundation Included in annual report to Board of Directors | Girls Power Administrator Include in Funding agency biannual progress report | Biannual progress report Girls Power annual report to funders and volunteers Peer-reviewed publication or presentation at professional meeting | Biannual progress report Girls Power annual report to funders and volunteers |
| Challenges What makes this measurement or evaluation difficult or expensive? | None | Participants may leave after signing attendance sheet. Signing in will consume time allotted for session. | Knowledge gain measured immediately after the session may not reflect long-term information retention Without grade or other incentive participants may submit random rather than serious responses. Girls Power does not have resources for Access database programming and analysis. This expense was not included in the budget. | Participants may cheat on urine screens to secure the program incentives. Staff require training and on-going monitoring to assure quality test results. | Other factors including racism impact pregnancy outcomes. The date will include non-participants. |