## Sheet1
Qualitative Risk Analysis
ID | Category | Risk Name | Risk Description | Risk Owner | Reason/Cause | Effect | Probability | Impact/Cost | Impact/Time | Impact/Quality | Risk Score | Risk Response Strategy | Cost
1 | Technical | Installation difficulties | Installation of the system might be different | IT personnel | Availability | Application not functioning as required | 5 | 4 | 4 | 2 | 4 | Hire experience IT experts to install the system. | 1000
2 | Organizational | Hard to get to know how the system works | The employees and management may not know how to use the system. | Project manager | Availability | failure in implementation | 5 | 2 |  | 4 | 4 | Train all employees on how the system work | 2000
1 | Organizational | Less funds to complete the project | The funds allocated for the project may not be enough. | Project manager | Availability | Incomplete implementation of the project | 3 | 4 | 5 | 4 | 3 |  | 1300
4 | Technical | Compatibility challenges | The technology may not be compatible with existing system and hardware. | IT personnel | Availability | Failure of the project | 2 | 4 | 2 | 3 | 1.6 | Purchase new hardware and optimize the software to fit | 5000
5 | Organizational | Difficult in customization | The software must be customaries to fit to organization needs, sometimes it difficult to full costomarization the functional requirements | Users | Availability | Poor service delivery or partial service delivery | 3 | 3 | 5 | 4 | 3 | Hire experts to do the customization | 1000
6 | Project Management | Late delivery of the project | Some task in the project may experience delays in the implementation. | Project manager | Availability | Delay of the project | 5 | 2 | 2 | 2 | 2 | Use realistic schedule for the project | 500
7 | External | Privacy issues in the software | Legal issues may arise due to use of personal information | Legal | Availability | Legal issues | 1 | 4 | 3 | 3 | 0.8 |  | 1200
8 | Project Management | Difficult in communication | There can be conflict among various parties such as developers and other stakeholders | Project manager | Availability | Poor implementation of the project | 3 | 4 | 4 | 2 | 2.4 | Design a communication plan for project | 3000
9 | Technical | Poor Design of the application interface | The interface may not satisfy the stakeholders | Designer | Availability | Low quality product | 2 | 2 | 3 | 1 | 1.2 | Involve all the stakeholders in the design of interface. | 1250
The risk score is calculated from the probability multiply by the highest risk score (1–5) divided by 5 to give an average risk score between 1 and 5.
Score between 4 and 5
Score between 2 and 3.99
Score between 0 and 1.99