## Template
Objectives | Success Measures |  | Verification | Assumptions
Goal: |  |  |  | To reach Goal:
The goal of this project is to make the opening of the new store in Colorado Springs memorable | The number of customers visiting the new store, satisfaction level of those customers and the profitability of the new store |  | Feedback from the visiting customers | Natural disasters and pandemics may significantly impact on the set goal of this project.
Purpose: |  |  |  | To reach Purpose:
The goal of this project is to open the 50th store in Colorado Springs in six months from today. | Completion of the project according to schedule, project falls within the budget, |  | Feedback from the executive managemnt. | Finances, government regulations and limmited resources
Outcomes: |  |  |  | To produce Outcomes:
The project managemnt seeks to make the opening of the new store memorable by accompanying it with lots of fanfare. Additionally, the team plans to equip the new store with full line of products from utensils to gourmet food items. | All the objectives have been met and good feedback from the customers visiting the new store |  | Statistics on visiting customers | Time constraints
Inputs: |  |  |  | To obtain & manage Inputs:
Action Steps | Resource | Budget | Due Dates
Identify and meet with stakeholders
Write a business plan
Register the new store | Financial resources | 1500 | This expected to take 1 week | Financial resources
Complete furnishing of the new store | Labor, financial resources, premises and equipment | 900000 | 4 months to completely furnish the new store | Scope constraints
Obtain licence, permits, and insurance to enagage at the new location | Financial resources | 4500 | 1 month for licencing | Government regulations
Establish relationships with vendors and suppliers | Industry know how | 2600 | 1 week | Competition in the market
Hire staff for the new store |  |  | 1 week | Supply and demand forces in the market, image of the organization, and competitors
Market the new store |  | 10000