## Question 9
Steps | Current Routine | Proposed Changes
1 | Problems with time keeping | A time schedule.
2 | Slow operations | Proposal of fast operations
3 | High rate of dsyfunctional conflict | Proposal to manage conflict
4
5
6
7
8

## Question 10
Management Plan Worksheet You do not need to fill out every cell in this worksheet - only those that are necessary for you to describe your project and make your management plan. However, please do fill all relevant cells. Further, you may add, adjust, or reformat this worksheet if doing so is a better fit.
ACTIVITIES TO COMPLETE PROJECT | BREAK DOWN ACTIONS | PEOPLE | HOW TO ENROLL | COORDINATION | TIMING | OBSTACLES | CONTINGENCY PLANS | FOLLOW UP
What activities must be performed in order to complete this project? | If more than one person or group is needed to perform this activity, break the activity down the specific actions they will perform. | Who needs to perform each action? | How will you get this person or group to commit to perform this action? How will you motivate them to perform it well? | How should the person or group who performs this action coordinate with people who perform the other actions or activities? | When does this step need to happen? | What, if anything, is likely to be difficult about this step? | What will people need to do to ensure that they overcome the obstacles they are likely to encounter? | How will you follow up with people who have committed to perform each action?
Activity 1: | 1.Setting a clear and simple objevtive for the meeting. | The meeting facilitator | Delegating authority to them. | Asking questions | Before the meeting | Agreeing to be responsible as the facilitator. | Be receptive | Asking for a report upon completion of task.
| 2.It can be done through analysis of the work place problems | The workplace counselor | Requesting them to be a moderator in the meeting. | using questionnaires | Before the meeting | Agreeeing to assume resonponsibility. | Be receptive | supervision of the task.
| 3. Deciding on the purpose of the meeting. | The workplace manager | By informing them about the importance of problem solving . | Questionnaires | Before the meeting | Agreeing with the decision to hold the meeting. | Be open minded | Asking questions concerning how the task was performed.
| 4. Brainstorming the ideas on how to collect greviances. | The employees | By promising to keep their issues private and anonymous. | Close ended questionnaires | Before the meeting | people opening up about their isuess | Be willing to open up. | Asking for responses about the activity.
5.
6.
Activity 2: | 1.identifying a location for the meeting | The meeting facilitator | Delegating authority to them to choose a suitable location. | Doing research on the requirements for a suitable meeting location. | Before the meeting | Finding a suitable location for the meeting. | Be willing to resaerch on different locations. | Requesting feedback on the chosen location.
| Decoration of the location | The meeting facilitator | Giving instructions on the requirements. | Doing research on the requirements for a suitable meeting location. | Before the meeting | Budgeting for the decoration of the location. | Be creative and alaytical. | Asking for a budget report for the decoration of the location.
3.
4.
5.
6.
Activity 3: | 3.Deciding a day and time for the meeting | The workplace manager | By requesting them to set a date for the meeting. | Analyzing work days that are the least busy. | Before the meeting | Finding a day to suit everyones work schedule. | Ask for sugesstions for which day is most suitable. | Requesting the employees take on the meeting.
2.
3.
4.
5.
6.
Activity 4: | 5.organizing refreshments for the meeting | The meeting facilitator | Asking for the preferences of people attending the meeting. | researching how to acess to the different preferences of refreshments . | Before the meeting | Acquring all the different preferences for the meeting attendants. | Avail refreshments that are common to most people. | Request for feedback concernig the refreshments.
2.
3.
4.
5.
6.
Activity 5: | conducting the actual meeting | The meeting facilitator | Requesting them to be arrive at the event early and stick to the set time. | Disseminating a time schedule for each activity prior to the meeting. | Before the meeting | Getting people to keep time. | Develop a penalty for anyone who fails to keep time. | Requesting feedback about the meeting.
| Keeping time | employees, managers, the cousleor, investors. | Requesting them to be early for the meeting and to avoid deviating from the main objective. | Disseminating a time schedule for each activity prior to the meeting. | During the meeting. | Getting people to keep time. | Develop a penalty for anyone who fails to keep time. | Requesting feeback about the impact of the meeting.
4.
5.
6.
Activity 6: | 1.
2.
3.
4.
5.
6.
Activity 7: | 1.
2.
3.
4.
5.
6.
Activity 8: | 1.
2.
3.
4.
5.
6.
Activity 9: | 1.
2.
3.
4.
5.
6.
Activity 10: | 1.
2.
3.
4.
5.
6.
1.
2.
3.
4.
5.
6.
1.
2.
3.
4.
5.
6.