Professor’s Name

Student’s Name

Course title

Date

Question 1

Solution

a).  Makespan  is 18 days.

b) : Machine idle times are : A - 9 hours, B - 8 hours, C - 7 hours

| Machine | Working Hours | Idle Hours |
| --- | --- | --- |
| A | 9 | 9 |
| B | 10 | 8 |
| C | 11 | 7 |

c)

Solution

Job completion is well before due dates.

| Job | Work center/Machine Hour | Due date | Delivery (Hours) |
| --- | --- | --- | --- |
| 1 | A/3 , B/2, C/2 | 3 | 9 |
| 2 | C/2 A/4 | 2 | 7 |
| 3 | B/6, A/1, C/3 | 4 | 18 |
| 4 | C/4, A/1, B/2 | 3 | 14 |

d).

Solution

Idle times are as follows.

| Job | Worker center/Machine Hours | Due Date | Delivery (Hours) | Waiting Time |
| --- | --- | --- | --- | --- |
| 1 | A/3 , B/2 ,C/2 | 3 | 9 | 0 |
| 2 | C/2, A/4 | 2 | 7 | 0 |
| 3 | B/6 ,A/1,C/3 | 4 | 18 | 6 |
| 4 | C/4,A/1,B/2 | 3 | 14 | 5 |

e).

Solution

Better priority schedule: 3-1-2-4 with timespan - 14 hours.

The idle time can be calculated using the finish time for each job - sum of machine hours -sum of changeover time

The above shows a efficient sequencing and changing this wont make a difference to makespan.

Question 2

a).  Draw a network for this project.

Solution

E

A						          G

B	               D

C			                            F

b).

Solution

Earliest Start (ES) = the earliest time when the activity can begin

Earliest Finish (EF) = ES + Activity Duration

Latest Finish (LF) = the latest time by when the activity can be finished without changing the project completion duration

Latest Start (LS) = LF - Activity Duration

Slack = LS-ES = LF-EF

Computing using the above gives us the below

Make a forward pass and a backward pass to determine ES, LS, and LF.

Activity Time            ES      EF        LS       LF     Slack

A	       3		0	3	0	3	0

B	       2		3	5	3	5	0

C	       5		0	5	0	5	0

D	       2		5	7	5	7	0

E	       4		3	7	3	7	0

F	       6		5	11	6	12	1

G	       5		7	12	7	12	0

(c)

Solution

Network Paths and their duration are -

AEG --> 3+4+5 = 12
ABDG --> 3+2+2+5 = 12
ABF --> 3+2+6 = 11
CDG --> 5+2+5 = 12
CF --> 5+6 = 11

Hence, critical path is the path with longest duration

Critical Paths are A-E-G, A-B-D-G, C-D-G