Merchandising Calendar

| Details | Specifications |
| --- | --- |
| Order no | 1233 |
| Style no | SP13009 |
| P.O no | 4565 |
| Order quantity | 10000 |
| Season | SS2019 |
| Fabric details | 100% cotton, plain woven, solid dyed fabric, 145 GSM |
| Product detail | Men’s formal shirt |
| Manufacturing country | Los Angeles, Ca |
| Destination port | New York, NY |
| Shipment port | Los Angeles, Ca |
| Buyer country | USA |
| Delivery date | 27th July 2019 |

| Number | Activity | Planned Date | Actual | Deviation (No. Of Days) |
| --- | --- | --- | --- | --- |
| 1 | Buyers inquiry and specification (proto kit) receives | 01-01-2019 |  |  |
| 2 | Pattern is made according to specification | 03-01-2019 |  |  |
| 3 | Proto sample submission | 05-01-2019 |  |  |
| 4 | Proto sample approval | 06-01-2019 |  |  |
| 5 | Order confirmation | 09-01-2019 |  |  |
| 6 | Trims and artwork sent for approval | 13-01-2019 |  |  |
| 7 | Lad dip sent for approval | 17-01-2019 |  |  |
| 8 | Requests for sample of trim and fabric sent | 03-02-2019 |  |  |
| 9 | Sample lot of trims entered into store | 04-02-2019 |  |  |
| 10 | Sample lot of finished fabric {yardage) entered into store | 13-02-2019 |  |  |
| 11 | Meeting with sampling and all other departments | 17-02-2019 |  |  |
| 12 | Fit samples sent to buyer | 26-02-2019 |  |  |
| 13 | Approval of fit samples | 05-03-2019 |  |  |
| 14 | Sales man samples sent to buyer | 10-03-2019 |  |  |
| 15 | Approval of sales man samples | 13-03-2019 |  |  |
| 16 | P.O raised by buyer | 15-03-2019 |  |  |
| 17 | Trims and artwork approved | 22-03-2019 |  |  |
| 18 | Approval of lab dip | 24-03-2019 |  |  |
| 19 | P.O raised for fabric and trims by merchandise/ sourcing team | 30-03-2019 |  |  |
| 20 | FPT sent to buyer | 09-04-2019 |  |  |
| 21 | Approval of FPT | 13-04-2019 |  |  |
| 22 | Ad/ photo shoot samples to buyer | 17-04-2019 |  |  |
| 23 | Approval of Ad/ photo shoot | 19-04-2019 |  |  |
| 24 | All fabric in-house | 21-04-2019 |  |  |
| 25 | All trims in-house | 22-04-2019 |  |  |
| 26 | Fabric and trim quality and quantity measured | 28-04-2019 |  |  |
| 27 | Size set samples sent to buyer | 01-05-2019 |  |  |
| 28 | Approval of size set samples | 03-05-2019 |  |  |
| 29 | GPT sent to buyer | 05-05-2019 |  |  |
| 30 | GPT approved by buyer | 07-05-2019 |  |  |
| 31 | Planned cut date | 16-05-2019 |  |  |
| 32 | Cut panes sent to embroidery | 20-05-2019 |  |  |
| 33 | Embroidery completed | 27-05-2019 |  |  |
| 34 | Pilot run | 02-06-2019 |  |  |
| 35 | Pre-production meeting | 04-06-2019 |  |  |
| 36 | PP sent to buyer | 06-06-2019 |  |  |
| 37 | Approval of PP samples | 07-06-2019 |  |  |
| 38 | Production start date | 12-06-2019 |  |  |
| 39 | Top samples sent to buyer | 14-06-2019 |  |  |
| 40 | Top sample approval | 19-06-2019 |  |  |
| 41 | production end date | 12-07-2019 |  |  |
| 42 | Finishing and packaging start | 13-07-2019 |  |  |
| 43 | Finishing and packaging completed | 15-07-2019 |  |  |
| 44 | Buyer quality audit | 17-07-2019 |  |  |
| 45 | Shipment sample sent to buyer | 19-07-2019 |  |  |
| 46 | Ex factory | 23-07-2019 |  |  |
| 47 | Ex country | 25-07-2019 |  |  |