Instructions – PLEASE READ THEM CAREFULLY

- The Assignment must be submitted on Blackboard (WORD format only) via allocated folder.

- Assignments submitted through email will not be accepted.

- Students are advised to make their work clear and well presented, marks may be reduced for poor presentation. This includes filling your information on the cover page.

- Students must mention question number clearly in their answer.

- Late submission will NOT be accepted.

- Avoid plagiarism, the work should be in your own words, copying from students or other resources without proper referencing will result in ZERO marks. No exceptions.

- All answered must be typed using Times New Roman (size 12, double-spaced) font. No pictures containing text will be accepted and will be considered plagiarism).

- Submissions without this cover page will NOT be accepted.

Learning Outcome:

- Understand the concept of process selection, forecasting, capacity planning, production forecast methods and schedule operations.

- Exercise critical thinking to analyze and synthesize information for scheduling operations and ERP.

- Develop numerical skills needed to analyze complex data of process design, quality management, capacity & scheduling planning to navigate in challenging situations.

- Create the capacity to write coherent project about actual operation management case studies.

.

Assignment Question(s):						(Marks 5)

Question 1:

Sequence the jobs shown below by using a Gantt chart. Assume that the move time between machines is one hour. Sequence the jobs in priority order 1, 2, 3, 4.

| Job Work Center/Machine Hours Due Date (days) |  |  |
| --- | --- | --- |
| 1 | A/3, B/2, C/2 | 3 |
| 2 | C/2, A/4 | 2 |
| 3 | B/6, A/1, C/3 | 4 |
| 4 | C/4, A/1, B/2 | 3 |

- Using finite capacity scheduling, draw a Gantt chart for the schedule (Marks 0.5)

- What is the makespan? (Marks 0.5)

- How much machine idle time is there? (Marks 0.5)

- How much idle time (waiting time) is there for each job? (Marks 0.5)

- When is each job delivered? (Marks 0.5)

- Which department is the bottleneck? (Marks 0.5)

- Calculate the machine utilization? (Marks 0.5)

Question 2:

A public accounting firm requires the following activities

for an audit:

| Activity | Immediate Predecessor | Activity time |
| --- | --- | --- |
| A | - | 3 |
| B | A | 2 |
| C | - | 5 |
| D | B, C | 2 |
| E | A | 4 |
| F | B, C | 6 |
| G | E, D | 5 |

- Draw a network for this project? (Marks 0.5)

- Make a forward pass and a backward pass to determine ES, LS, EF, and LF? (Marks 0.5)

- What are the critical path? (Marks 0.5)

Answer: