Network Diagram

Student Name

Institutional Affiliation

A

B

C

D

E

F

G

H

I

J

CRITICAL PATH = A=B=C=G=I=J

CRITICAL PATH =3, 4, 4, 2, 2, 1= Summation = 15 days

| 7 | D | 8 |
| --- | --- | --- |
| 10 | 1 | 11 |

| 7 | C | 11 |
| --- | --- | --- |
| 7 | 4 | 11 |

| 0 | A | 3 |
| --- | --- | --- |
| 0 | 3 | 3 |

| 3 | B | 7 |
| --- | --- | --- |
| 3 | 4 | 7 |

| 11 | G | 13 |
| --- | --- | --- |
| 11 | 2 | 13 |

| 13 | I | 15 |
| --- | --- | --- |
| 13 | 2 | 15 |

| 15 | J | 16 |
| --- | --- | --- |
| 15 | 1 | 16 |

| 7 | E | 8 |
| --- | --- | --- |
| 11 | 1 | 12 |

| 11 | H | 12 |
| --- | --- | --- |
| 12 | 1 | 13 |

| 7 | F | 10 |
| --- | --- | --- |
| 9 | 3 | 12 |

Total slack= total time the project gets delayed without interfering with the critical path

Total slack= summation of slacks not on the critical path

Total slack= D+E+F+H

Total slack=3+4+1=8 days

It is possible to delay the project by 8 days without interfering in the end date.

The project would be completed by the fifteenth date, which means that the project would be awarded the bonus pay of 500 dollars.

I would not mind seeking additional help to work in either roofing or the framing portion of the project as they last 4 days each. The additional help take up $ 120, which is easily catered by the bonus pay of $ 500.

Key information

A= FOUNDATION

B=FRAME

C=ROOF

D=WINDOWS

E=DOORS

F=ELECTRICALS

G=DRYWALL

H=OPENER

I=PAINT

J=CLEANUP