Nightingale Project—A

1. Will the project as planned meet the October 25th deadline?

The project is supposed to start on January 2, 2017 and meet the October 25th deadline. The number of days from January 2 to October 25 is 297. The total number of weekends and holidays is 95 days. Therefore, the available number of days is 202 days. Based on the critical path of the project, the minimum number of days that would be needed to complete is 220 days. Therefore, the project will not meet the October 25th deadline.

2. What activities lie on the critical path?

The critical activities are shown in red in the gantt chart.

The activities are as follows: 1-4-10-16-18-20-21-22-23-24-25-27-28-29-30

3. How sensitive is this network?

The sensitivity of a project indicates the possibility of having multiple critical paths. This project is barely sensitive because it has only one critical path. Besides, the slacks of the non-critical activities are quite significant. There is no possibility of these activities becoming critical even when their duration is reduced. In addition, the absence of sensitivity in the project’s network can be alluded to the fact that the transition from the normal time to optimum time would not lead to new critical activities.