## Slide 1: Body-Worn Cameras Program
Event
Date May 2, 2021
Presenter: Shanta Oliver
Organization

## Slide 2: BWC Program Objectives
To increase transparency, accuracy and reliability of information on police/public interaction
To develop a system that provide audio and video technologies to be worn by uniformed officers
Develop a digital data management system to secure collected information
Develop and implement strong policies to ensure proper and credible use of BWCs.
Notes: There are several reasons for adopting BWCs:
  To produce more and better evidence to facilitate fighting crime more efficiently.
  View footage to get the reports accurate. Storage of evidence.
  To help make law enforcement more transparent in its interactions with the public will help build public trust in our law enforcement agency (Wright & Brown, 2020)

## Slide 3: Project Outline
Identify and solicit input from all stakeholders
Develop policy that address legal and privacy
Identify and contract appropriate vendors to supply required resources
Train officers on the usage of BWC
Roll out the program in phases
Notes:   Including community and advocacy organizations in the planning and policy development phases of BWC programs has positive results. It will enhance public perceptions of transparency and aid in resolution of controversial issues concerning privacy, activation, review of footage.
  Meanwhile,
  Concerns about police filming of vulnerable and sensitive populations – juveniles, people in distress, domestic violence situations, and child molestation and child sexual assault cases (Taylor & Lee, 2019)

## Slide 4: Project Phase: Initiation
Deliverables
Establish Executive Management Team
Identify Key Stakeholders
Research BWC technology
Develop Project Charter
Approval of Project Charter by Mayor
Notes: Without sound and collaboratively developed policies BWCs will likely cause more problems than they resolve. We should take caution to collaborate with stakeholders that everyone understands, police can implement and articulate Bureau of Justice Assistance (2020). BWC policies should also provide specific instructions on when activation, usage and adoption. We will not mandate recording of all situations due to privacy concerns.
Think; Here is what we should have
  A sound policy (Kalle & Hammock, 2020).
  Adequate training.
  Continuous supervision.
  Community education and buy-in. Most important!!!!

## Slide 5: Project Phase: Planning
Develop Risk Plan
Develop budget (Capital & Operating Cost)
Form Policy Development Team
Outline Implementation Schedule
Communicate Plan to Stakeholders
Notes: Generally, we should have a comprehensive planning process in place to guide policy development and BWC implementation. I shall oversee a multidisciplinary working group comprising of representatives from IT, advocacy groups, community stakeholders, local government, and prosecution (Wright & Brown, 2020).
Planning should note that storage of data is costly, when packed with services for redaction, data sharing, data management, and software and hardware upgrades (Taylor & Lee, 2019).
We must be realistic about costs. There are one-time costs like purchasing cameras and related equipment. Also take note of storage costs and equipment upgrades, and replacement. A good vendor contract should help to off set these burdens.

## Slide 6: Project Phase: Execution
Delivery of training
Deployment of Cameras
Implementation of control measures on privacy
Data collection plan for independent project evaluation
Implementation of Data Management System
Notes: This will happen in phases beginning with a control program to see how officers perform. Feedback form the officers and the public will be critical before full roll out to have a useful program. The phased rollout is crucial to examine emerging issues in BWC practice and implementation.
Storage of BWC data and footage is an ongoing concern.
  Generally, we should expect storage costs to fall with as technology improvements such as cloud storage
  Hybrid storage systems will also come in handy.

## Slide 7: Project Milestones
Milestone | Deliverables | Responsibility | Date
1. Project Initiation | Develop Project Charter Research BWC technology Identify Key Stakeholders | Shanta Oliver | June 2021
Notes: Does our agency have the necessary technological infrastructure for BWCs. The initiation phase is important to shape the direction of the project and overcome challenges of visibility, procedural justice, and legitimacy (St. Louis, Saulnier & Walby, 2019)
Some questions to ponder about include how do we properly plan and implement an effective BWC program?
Which administrative policy and training methods to adapt. Where to borrow assistance and information sharing.

## Slide 8: Milestones
2. Project Planning | Develop BWC Project Plan Solicit Stakeholder Input Risk Assessment Vendor Selection Awarding Consultant Contract Budgeting Implementation Schedule Present plan for Mayor’s Approval Stakeholders Communication Plan | Project Leader and Representatives from IT; | End of July, 2021
Notes: Here are some questions at this stage
How do we introduce community groups to the program redeployment and the planning process (Hodge Jr & Ortiz, 2021)? There is need to let community groups have a chance to voice concerns/ask questions for better collaboration (Wright & Brown, 2020).
Also give a chance to the community to review the agency’s administrative policy and possibly publish it to make it publicly available.
Also during planning we should know how to “market” the BWC program both internally and within the community to get maximum support. This equals success on rollout!!

## Slide 9
3. Policy Development | Form Policy Development Team Solicit Stakeholder Input on ethical issues | Kevin Tosh | End of December, 2021
4. Project Funding | Approval of funding from City Council | Director of Budget | January, 2022
5. Technology Solution Evaluation and Selection | Evaluation of cameras based on field testing Vendor Selection | IT Department | February, 2022
Notes: Funding and technology selection will follow basic infrastructure necessary to support BWC program. Information technology (IT) concerns when making selection include – room and capacity for supporting multiple stations; information processing speed to support timely upload of footage from devices and, creating links for live recording and transmission for efficient management of new data.

## Slide 10
6. Submission to City Council | Submit to council for approval to enter into a contract with the selected vendor | Wayne Harris | January, 2022
7. Contract Negotiations | Execution of contract | Legal Department | January, 2022
8. Phase I Trials | BWC Training Limited deployment and continuous training Continuous CPSI evaluation | Shanta Oliver | February 2022
Notes: There is need to get the Mayor to support our program. He is willing to do so already. Get the best contracts and proceed to a trail phase. The guidelines by the Bureau of Justice Assistance and U.S Department of Justice will help in rolling out our program on time (Bureau of Justice Assistance, 2020).

## Slide 11
Phase 2 Implementation | Continuous BWC Training Capacity increase by 50% Implementing views from the public Reviewing performance | Entire team participation | May 2022
Notes: Paying special attention to the issue of community engagement in BWC planning and policy development. We will ask a series of questions to illustrate how important we think community engagement is regarding BWCs, especially when issues of transparency and trust are paramount (Hodge Jr & Ortiz, 2021).
Issues include when to record since this is a significant consideration when drafting the policy and the limited circumstances deterring recording (St. Louis, Saulnier & Walby, 2019).

## Slide 12
Full Scale Roll out | 100% rollout Continuous feedback from public Continuous monitoring to make improvements Analyze changes in gathering evidence | Entire team participation | October 2022
Notes: BWCs show great promise for helping police officers provide more accurate reports, for assisting in investigations, and for increasing police accountability (St. Louis, Saulnier & Walby, 2019).
Our BWC program is a crucial additional tool at the department’s disposal to reduce crime, record evidence and assist in nailing culprits in courts.
Remember Full scale roll-out of BWC's will require:
  A sound policy with regards to the law and ethical practices.
  Adequate training for everyone.
  Constant supervision. Don’t worry about. We must get it right!
  Community education and buy-in (Wright & Brown, 2020).

## Slide 13
References
Bureau of Justice Assistance (2020). Body-Worn Cameras (BWCs). U.S Department of Justice. https://bja.ojp.gov/program/body-worn-cameras-bwcs/overview
Hodge Jr, S. D., & Ortiz, R. (2021). Police body cameras - A lesson in objectivity and accountability or a tool without a scientific basis? Richmond Journal of Law & Technology, 27(2), 1–51.
Kalle, A., & Hammock, G. (2019). Bias in video evidence: Implications for police body cameras. Applied Psychology in Criminal Justice, 15(2), 118–140.
St. Louis, E., Saulnier, A., & Walby, K. (2019). Police use of body-worn cameras: Challenges of visibility, procedural justice, and legitimacy. Surveillance & Society, 17(3/4), 305–321. https://doi.org/10.24908/ss.v17i3/4.8649
Taylor, E., & Lee, M. (2019). Off the record? Arrestee concerns about the manipulation, modification, and misrepresentation of police body-worn camera footage. Surveillance & Society, 17(3/4), 473–483. https://doi.org/10.24908/ss.v17i3/4.6550
Wright, J. E., & Brown, H. (2020). What matters more? Police or the community for body worn camera policy. Public Administration Quarterly, 44(3), 462. https://doi.org/10.37808/paq.44.3.5