Operational Plan: Template

Objective: Recruit Dr. Oz to practice at our facility	 Outcome: Increasing patient volume by 25% within 3 months.

| Strategies | Projects/Activities | Time Frame | Persons Involved | Budget Estimated |
| --- | --- | --- | --- | --- |
| Contact Dr. Oz | - Research what talent agency or management company represents Dr. Oz - Check licensed specialties of Dr. Oz (find the most beneficial way to implement his presence). - Pitch proposed idea and secure his participation | 1week 3 days 4 days | Project Manager CEO CEO Board of Trustees | Salary for Dr. Oz $10,000 per month |
| Set up a meeting to implement contract | - Get schedules of key members of the organizational team - Include legal counsel (discuss any specifics we need to understand prior to securing a contract with Dr. Oz) | 1 day 2 days | Project Manager Administrative Assistant COO Legal Department | Legal fees $5,000 to $8,000 |
| Produce marketing materials for the new provider | - Purchase commercial ad space - Source commercial production companies - Design, order and distribute printed materials | 1 day 1 week 1 week | Project Manager Marketing Department External Contractors | TV ads $8,000 Production costs $1,500 Material costs $ 2,300 per month |

TOTAL MONTHLY COSTS: $ 34,800