Chapter 13- Exercise 3

At the end of period 4, 100% of task A would be completed. The percentage work completion for task B, C, D and E would be 50%, 33%, 0% and 0% respectively. The earned value (EV) for task A would be $400. Task A would also have $300 Actual cost (AC), $400 Planned value (PV), $100 Cost variance (CV) and $0 Schedule variance (SV). The EV, AC, PV, CV and SV for task B would be $900, $1000, $800, $-100 and $100 respectively. Task C will have EV of $533, AC of $500, PV of $600, CV of $33 and SV of $-67. The EV, AC, PV, CV and SV for tasks D and E would all be $0 at the end of period 4.

The end of period 8 also has interesting statistics with regards to the six tasks. Tasks A, B and C would be 100% complete while task D would be 25% complete, task E would be 33% complete and task F be 0% complete. The EV, AC, PV, CV and SV for task A would be $400, $300, $400, $100 and $0 respectively. Task B will have EV of $800, AC of $2200, PV of $800, CV of $-1400 and SV of $0. Task C will have EV of $600, AC of $1500, PV of $600, CV of     $-900 and SV of $0. With regards to Task D, its respective EV, AC, PV, CV and SV would be $0, $300, $0, $-300 and $0 respectively. Task E will have EV of $0, AC of $300, PV of $0, CV of $-300 and SV of $0. The EV, AC, PV, CV and SV for task F would be $0 at the end of period 8.