# PROJECT COMPENDIUM

# BSBPMG511 –PROJECT CONCEPT/brief

Project NAME: Covid -19 Vaccine Development Project

PROJECT TEAM …………………….

Student name:

Student number

Contents

PROJECT COMPENDIUM	1

BSBPMG511 –PROJECT CONCEPT/brief	1

Background/Context	2

Budget	3

Objectives	3

Target Outcomes	3

How will the success of the project be measured?	4

Output(s)	4

Governance & Reporting Requirements	4

Resources	4

Stakeholders & Communication Strategy	5

Schedule/Timeframes	6

Assumptions and Constraints	6

Major Risks & Minimization Strategies	6

PART 2: PROJECT ACTIVITIES & MILESTONES	7

DOCUMENT ACCEPTANCE AND RELEASE NOTICE	8

## Background/Context

The world is undergoing an unprecedented times due to the current novel COVID-19 .The World Health Organization is trying to draw lessons learnt from the global impact of other related disease outbreaks in the past.

This project will help researchers and scientists in developing a practical plan for ensuring a vaccine has been approved for human use. The vaccine will be developed in three major stages before approval and being licensed .After approval WHO will grant rights for immunization to commence globally as per the approved routine programs

Immunization is a cost-effective method for controlling spread of infectious disease in the public health sector. There are two major types of immunization; routine immunization and mass campaigns. Vaccine distribution will also be closely monitored by all agencies and stakeholders to ensure it is evenly distributed and within the right quality checks.

Different countries may consider developing an introduction plan for lower administrative levels in the country that translates goals and activities articulated at the national level into ones more relevant at sub-national level.

## Budget

The proposed project budget covers the general immunization financing from the specific country’s, WHO and donor funding, as applicable

| Vaccine Development Tasks | Cost ( $ ) |
| --- | --- |
| Planning Stage | 16,000.00 |
| Exploratory Stage | 30,000.00 |
| Pre-Clinical Stage | 20,000.00 |
| Investigational New Drug (IND) Application | 10,000.00 |
| Clinical Studies with Human Subjects | 25,000.00 |
| Phase I Vaccine Trials | 40,000.00 |
| Phase II Vaccine Trials | 45,000.00 |
| Phase III Vaccine Trials | 48,000.00 |
| Approval and Licensure | 55,000.00 |
| Post-Licensure Monitoring of Vaccine | 15,000.00 |
| Phase IV Trials | 20,000.00 |
| TOTAL |  |

## Objectives

This vaccine development project is meant to provide suggestions and guidelines  for key areas to be considered, and as such, may be missing some items relevant to a particular country or to a particular vaccine introduction, or equally may contain some items that are not relevant. Each country and vaccine introduction will have different characteristics and requirements, and thus each country’s introduction plan will need to be adjusted accordingly.

## Target Outcomes

The Covid 19 vaccine project will include short-, intermediate- and long-term targets all aligned with the Who guidelines and timelines for the vaccine production and distribution which include;

- Develop new and improved vaccines which are readily available globally.

- Guarantee a stable supply chain system for the vaccine from all the manufacturers to all countries as required for public health preparedness

- Ensure improved human vaccine safety system through surveillance and strengthening management information systems related to production and distribution

- Promote well informed vaccine decision-making strategies by all manufacturers.

## How will the success of the project be measured?

The success of this project will be determined by the ability of the team to deliver the vaccine in due time with utmost quality and within budget to meet the target outcomes.

## Output(s)

The project strives to put in place a framework that aims to assess performance and to provide required guidance to track resource allocation on the Covid -19 vaccine project from start to finish by proper planning of the overall process of determining how, when and which project deliverables are required to achieve a successful project.

## Governance & Reporting Requirements

## Resources

Project resource monitoring involves analyzing all indicators against resources allocated for a particular task to ensure accountability and transparency in the COVID-19 Vaccine Development. The major resources assigned in the project will be as shown in the below project excerpt.

|  | Resource Name | Type | Initials | Max. Units | Std. Rate | Ovt. Rate | Cost/Use | Accrue At |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | WHO Representatives | Work | W | 100% | $55.00/hr | $82.50/hr | $0.00 | Prorated |
| 2 | Scientists | Work | S | 100% | $55.00/hr | $82.50/hr | $0.00 | Prorated |
| 3 | Lawyers | Work | L | 100% | $78.00/hr | $117.00/hr | $0.00 | Prorated |
| 4 | Management 1 | Work | M | 100% | $51.00/hr | $76.50/hr | $0.00 | Prorated |
| 5 | Secretary 1 | Work | S | 100% | $18.00/hr | $27.00/hr | $0.00 | Prorated |
| 6 | Doctor 1 | Work | D | 100% | $71.00/hr | $106.50/hr | $0.00 | Prorated |
| 7 | Nurse 1 | Work | N | 100% | $52.00/hr | $78.00/hr | $0.00 | Prorated |
| 8 | Lab Technician 1 | Work | L | 100% | $18.00/hr | $27.00/hr | $0.00 | Prorated |
| 9 | Doctor 4 | Work | D | 100% | $71.00/hr | $106.50/hr | $0.00 | Prorated |
| 10 | Project Team | Work | P | 100% | $0.00/hr | $0.00/hr | $0.00 | Prorated |

## Stakeholders & Communication Strategy

STAKEHOLDER REGISTER

|  | NAME OF THE STAKEHOLDER | GENERAL ROLE | ROLE IN THE PROJECT | TYPE |
| --- | --- | --- | --- | --- |
| 1 | Government. | Increase support for national immunization programs | Ensure full collaboration regionally and internationally and provide public awareness as required | External |
| 2 | WHO (World Health Organization) | Providing supportive information and vaccine analysis | Approval and licensure | External |
| 3 | Project manager | Responsible for executing decision by senior management | Responsible for completing the project development on time | Internal |
| 4 | Doctors | Assessing the type of human immune generated by the vaccine | Assess prevention of infection by any targeted Pathogen Conducting randomized studies relating the vaccine from stage to stage | Internal |
| 5 | Researchers | Providing a multidisciplinary research based analysis that impact based and results oriented | Ensuring publication of science based evidence relating to the vaccine | Internal |
| 6 | Manufacturers and distributors | Manufacturing and production. | Continuous manufacturing, production and supply of approved high quality vaccines. | External |

## Schedule/Timeframes

A successful project should have a definite start and finish date which are tracked on progress to avoid delays, the table below shows a proposed time allocation schedule for the project.

| Vaccine Development Tasks | DURATION (DAYS) | START | FINISH |
| --- | --- | --- | --- |
| Planning Stage | 10 |  |  |
| Exploratory Stage | 15 |  |  |
| Pre-Clinical Stage | 20 |  |  |
| Investigational New Drug (IND) Application | 15 |  |  |
| Clinical Studies with Human Subjects | 10 |  |  |
| Phase I Vaccine Trials | 20 |  |  |
| Phase II Vaccine Trials | 10 |  |  |
| Phase III Vaccine Trials | 10 |  |  |
| Approval and Licensure | 5 |  |  |
| Post-Licensure Monitoring of Vaccine | 15 |  |  |
| Phase IV Trials | 20 |  |  |
| TOTAL DAYS | 150 |  |  |

## Assumptions and Constraints

Assumptions are unforeseen events that are expected to happen during the vaccine development lifecycle. Some of the assumptions considered in this project are;

There will be adequate financing which will be done on time and when required. All the professionals involved will have the required skills know how to develop the vaccine and help in timely distribution to all countries.

## Major Risks & Minimization Strategies

Risk management tools such as identifying risks, mapping out impacts, planning project responses will be deployed to identify risks and develop a risk register with mitigation strategies against them.

The table below shows some of the foreseen risks and their respective mitigation plans.

| Risk Description | Owner | Mitigation Action |
| --- | --- | --- |
| Project going over budget | Project Team | Monitor all cost drivers. |
| Vaccine failure resulting in death | Project Team | Monitor all test subjects and note physical and mental changes. |
| Allergic reactions in test subjects | Doctors | Develop an antidote to the allergic reactions. |
| Drug interactions with Vaccines | Doctors | Conduct thorough analysis of testers' drug history and pre-existing conditions. |
| Wrong test administration | Doctors, Nurses | Proper training of all professionals involved |

## PART 2: PROJECT ACTIVITIES & MILESTONES

| No | Description | WHO | Scheduled Start | Scheduled Finish | Predecessor |
| --- | --- | --- | --- | --- | --- |
| 1 | Planning Stage | World Health Organization | 11/28/2020 | 12/28/2020 |  |
| 2 | Exploratory Stage | Researchers | 11/1/2021 | 2/12/2021 | 2 |
| 3 | Pre-Clinical Stage | Researchers and Doctors | 3/15/2021 | 4/28/2021 | 2 |
| 4 | Investigational New Drug (IND) Application | Medical practioners | 4/28/2021 | 4/31/2021 | 1 |
| 5 | Clinical Studies with Human Subjects | Researchers and Doctors | 4/31/2021 | 5/15/2021 | 4 |
| 6 | Phase I Vaccine Trials | Researchers and Doctors | 4/31/2021 | 5/15/2021 | 5 |
| 7 | Phase II Vaccine Trials | Researchers and Doctors | 5/15/2021 | 5/20/2021 | 6 |
| 8 | Phase III Vaccine Trials | Researchers and Doctors | 5/21/2021 | 5/30/2021 | 7 |
| 9 | Approval and Licensure | WHO and National governments | 5/31/2021 | 6/10/2021 | 8 |
| 10 | Post-Licensure Monitoring of Vaccine | WHO and National governments | 6/11/2021 | 6/20/2021 | 9 |
| 11 | Phase IV Trials | World Health Organization | 6/21/2021 | 6/30/2021 | 10 |

## DOCUMENT ACCEPTANCE AND RELEASE NOTICE

PREPARED:	DATE:___/___/___

(for acceptance)	(<Student name>, <Project Title> Project Manager)

ACCEPTED:	DATE:___/___/___

(for release)	(Project Sponsor, <name, TRAINER>)