## Sheet1
SECTION | PURPOSE | TASKS
|  | NAME OF TASK | DESCROPTION OF TASK | TARGET COMPLETION DATE | DELIVERABLES | TO WHOM | DUE DATE | DELIVER DATE
I - Introduction | Preparation of a project plan and a Gantt chart for the project. | Preparation of project plan | Familiarization with requirements | 2019-01-29 | Completed project plan | Board of managers at Sharp Medical center | 2019-01-30
Project plan draft
Completion of project plan
|  | Gantt chart | Preparation of a Gantt chart | 2019-01-29 | Gantt chart | Board of managers at Sharp Medical center | 2019-01-30
II - Emergency Department Documentation and Audit | Audit of the ED's medical records in preparation for an upcoming survey by the Joint Commission. | Preparation for the Joint Commission survey | Securing the data | 2019-02-10 | A memo of the completed audit results agaaint the Joint Commission's documentation requirements. | Dr. Wolkerson | 2019-02-13
Determination of Joint Commission documentation requirements
Review of ED records and audit of representative cases
Analysis of components
Compilation of results
|  | Preparation for the ED's transition to an electronic records system | Creation of a screen design encompassing data documentation elements | 2019-02-11 | Screen design | Canvas platform | 2019-02-13
III - Establishment of a Comprehensive Query Process | Review of the query process policies and procedures and query templates with a view of aligning them to current fuidelines | Review of query process in the EHR | Review of the query process in HER | 2019-02-16
|  | Review of query policy, query escalation policy, and query audit policy | The Policy and Procedure (P & P) subcomittee will review these policies | 2019-03-08 | P & P review report | Canvas platform | 2019-03-11
|  | Update of query templates | Present on admission | 2019-03-08 | Completed reviewed query templates | Canvas platform | 2019-03-11
Sepsis
Pneumonia and respiratory infection
Intraoperative or post-procedural complication
IV - Determination and Implementation of CDI Program Metric Reporting | Determination of the CDI reports that would be most useful to the hospital administration and healthcare workers | Develop a report for administration and physician leadership relating to query answer rate | Review and analyze CDI reports most useful to staff | 2019-03-12
|  |  | Develop a report for administration and physician leadership relating to query answer rate | 2019-03-15 | Written report | Management of Sharp Medical Center | 2019-03-20
|  | Presentation of query report | PowerPoint presentation of query report | 2019-03-17 | PowerPoint presentation | Management of Sharp Medical Center and on the Canvas platform | 2019-03-20
|  | Recommendations | Proposition of corrective action plans and performance benhcmarks for query response issues | 2019-03-18 | Report | Management of Sharp Medical Center | 2019-03-20
V - Audit Potential Compliance Issues | Completion of a recovery audit plan for malnutrition and debridement | Malnutirion audit | Identification of major compliance issues, review of these issues, and proposition of potential solutions | 2019-03-25 | Audit report | Management of Sharp Medical Center | 2019-04-03
|  | Debridement audit | Identification of major compliance issues, review of these issues, and proposition of potential solutions | 2019-03-30 | Audit report | Management at Sharp Medical Center | 2019-04-03
|  | Policy and procedure | Development of policy and procedure relating to ongoing audits based on AHIMA Code of Ethics and Regulatory Standards | 2019-04-02 | Policy and procedure report | Management at Sharp Medical Center | 2019-04-03
VI - Physician and other staff Education | To enlighten staff on the procedures of the CDI program and the program's utilization | CDI Staff Education | Method of determining staff competency | 2019-04-15 | Completed PowerPoint presentation | Management at Sharp Medical Center | 2019-04-17
Narrated PowerPoint presentation
|  | Physician education | Method of determining staff competency | 2019-04-15 | Completed PowerPoint presentation | Management at Sharp Medical Center | 2019-04-17
Narrated PowerPoint presentation