## Basic Gantt Chart
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
| Budget Allocation | 2018-01-05 | 2018-03-08 | 0 | 63 | Nathan | 100%
| Market Research | 2018-02-18 | 2018-05-19 | 44 | 91 | Meredith | 80%
| Design | 2018-03-21 | 2018-09-23 | 75 | 187 | Brandon | 60%
| Manufacture and production | 2018-09-27 | 2019-03-29 | 265 | 184 | Michael | 40%
| Marketing Campaign | 2019-04-08 | 2019-06-23 | 458 | 77 | Rachel | 20%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1