## Slide 1: Project Assessment
Student Name
Institution Affiliation

## Slide 2: Project Assessment Calculations
Schedule Variance (SV)
SV = Earned Value (EV) – Planned Value (PV)
EV = $600
PV = $560
SV = 600 – 560
SV = $40

## Slide 3: Project Assessment Calculations
Cost Variance (CV)
Cost Variance (CV) = Earned Value (EV) – Actual Value (AV)
EV = $600
AC = $650
CV = 600 – 650
CV = -$50

## Slide 4: Project Assessment Calculations
Schedule Performance Index (SPI)
SPI = EV/PV
EV = $600
PV = $560
SPI = 600/560
SPI = 1.0714

## Slide 5: Project Assessment Calculations
Cost Performance Index (CPI)
CPI = EV/AC
AV = $600
AC = 650
CPI = 600/650
CPI = 0.9231

## Slide 6: Project Assessment Reflection
The project is ahead of schedule since from the calculations; we found that the schedule variance i=of the project being positive. Considering that the earned value of this project is higher than the planned value, we can precisely say that the project is doing quite well. However, the project is operating at a budget that is higher than the initially planned budget. The negative Cost Variance indicates this.
Additionally, the schedule performance index which is greater than one in this project indicates that the project is ahead of the planned schedule. Generally, the schedule performance index is used in projects to evaluate whether the project is operating within the planned schedule hence giving a prediction of the project getting completed within the scheduled time. In this project, the schedule performance index precisely indicates that the project is ahead of the planned schedule and hence it will be completed within the planned schedule. The cost performance index is used in the project to indicate how well the project is remaining or operating within the budget. The cost performance index, in this case, is less than one which indicates that the project is earning less than the amount spent.

## Slide 7: Reference
Czarnigowska, A., Jaskowski, P., & Biruk, S. (2011). Project performance reporting and prediction: extensions of Earned value management. International journal of business and management studies, 3(1), 11-20.