# Project Charter

Project Title: 	Delivery of prescriptions and drugstore items by flying drone

Project Start Date: 5th January 2019	 Projected Finish Date: 30th November 2019

Budget Information: The project is set to take a maximum of $1,750,000

Project Manager:

Philip Greenberg

+1355730-03903

phgreenbergin@gmail.com

Your Name (Insert your name here)

+177820-737878 (Replace this with your own phone number)

operations@hollingtons.com

Name, phone, e-mail

Project Objectives: To enable delivery of prescriptions and drugstore items to customers by using flying drones within the San Bruno, CA area which is the home location of the InDepthDrones organization.

Main Project Success Criteria: The main Success Criteria is carrying out a piloting project for the project to see how things work before fully launching it into operations and ensuring availability of the startup capital for the project before it begins.

Approach: The approach is to ensure success for the project is to ensure sufficient coordination between Hollington’s and InDepthDrones for appropriate and smooth running of the project for successful deliveries of the drugstore items and prescriptions. This will be enabled by sufficient communication between the two companies and putting in place a confirmation process to ensure that only eligible customers enjoy the service of the project to avoid delivery issues.

Roles and Responsibilities

| Role | Name | Organization/ Position | Contact Information |
| --- | --- | --- | --- |
| Overall oversight of the project operations at InDepthDrones Corporation | Jordan Kempler | InDepthDrones Corporation/ CEO and Founder | +1275-47477 |
| Collaborating with Hollington’s project manager to ensure coordination between the teams on both sides. | Phillip Greenberg | InDepthDrones Corporation/ Project Manager | +13730-0303 |
| Analyzing the business performance for InDepthDrones Corporation | Stephanie Williams | InDepthDrones Corporation/Senior Business Analyst | +14256-5627 |
| Ensuring proper functioning of systems and programs for his organization | Gerald Hasper | InDepthDrones Corporation/ Senior Systems Engineer | +15373-6728 |
| Overseeing the team for InDepthDrones Corporation | Eileen Seymour | InDepthDrones Corporation/ Project Lead, IT Systems | +18893-6773 |
| Overseeing the smooth running of the project operations, packaging, order processing etc. | Willis Jackson | Hollington’s/ Operations VP | +127454648 |
| Handling information regarding the project and communicating to the CEO and project manager | James Connor | Hollington’s/ Chief Information Officer | +198367356 |
| Working with the InDepthDrones Corporation Project lead to ensure proper coordination between the teams on both sides. | Mary Pearson | Hollington’s/ Project Lead, Business Operations Team | +190373656 |
| Working with the InDepthDrones Corporation Project lead to ensure proper coordination between the teams on both sides. | William Scott | Hollington’s/ Project Lead, Security Team | +178379486 |
| Ensuring processing of orders, packaging and order dispatch at store number 35864 | Julie Green | Hollington’s/ Pharmacy Manager Store #35864 | +198767867 |
| Ensuring processing of orders, packaging and order dispatch at store number 32185 | Steve Haskell | Hollington’s/ Pharmacy Manager Store #32185 | +13327288 |
| Ensuring processing of orders, packaging and order dispatch at store number 38734 | James O’Donnell | Hollington’s/ Pharmacy Manager Store #38734 | +18566782 |
| Ensuring processing of orders, packaging and order dispatch at store number 33001 | Wilma Marcy | Hollington’s/ Pharmacy Manager Store #33001 | +18917363 |
| Determining team members for the final project planning | You (Insert your name here in this box) | Hollington’s/ Project Manager | +18272626 |
| Analyzing the business performance for Hollington’s | Mary Kerstner | Hollington’s/ Business Systems Analyst | +16888929 |
| Working with William Postner to ensure system programs for placing orders run smoothly | Jonathan Perry | Hollington’s/ Programmer | +14367383 |
| Guiding Jonathan Perry to ensure system programs for placing orders run smoothly | William Postner | Hollington’s/ Senior Programmer | +83736365 |
| Managing computer databases to ensure safety of customer data stored | Sherry Loganthorpe | Hollington’s/ Database Administrator | +165672828 |
| Generating analysis reports for the organization | Linda Thornton | Hollington’s/ Reports Systems Programmer/Analyst | +153637373 |
| Ensuring the project is tested before launching through project piloting | Gerald Peritoni | Hollington’s/ Testing Specialist | +167383838 |
| Ensuring the project is tested before launching through project piloting | Elizabeth Walton | Hollington’s/ Senior Testing Specialist | +134243674 |
| Suggesting and evaluating changes in the operations to ensure success of the project | Shirley Johnson | Hollington’s/ Change Management Coordinator | +157383894 |
| Providing the funds and overseeing all aspects of the initiative | George |  | +123456789 |

Sign-off:

| NAME | SIGNATURE |
| --- | --- |
| Jordan Kempler |  |
| Phillip Greenberg |  |
| Stephanie Williams |  |
| Gerald Hasper |  |
| Eileen Seymour |  |
| Willis Jackson |  |
| James Connor |  |
| Mary Pearson |  |
| William Scott |  |
| Julie Green |  |
| Steve Haskell |  |
| James O’Donnell |  |
| Wilma Marcy |  |
| You (Insert your name here in this box) | (Put your signature Here) |
| Mary Kerstner |  |
| Jonathan Perry |  |
| William Postner |  |
| Sherry Loganthorpe |  |
| Linda Thornton |  |
| Gerald Peritoni |  |
| Elizabeth Walton |  |
| Shirley Johnson |  |
| George |  |

Comments: Determined to work together for success of this project through hard work, honesty, diligence and respect for one another and for company.