## Sheet1
Activity | Description | Tasks |  | Immediate Predecessors | Optimistic Duration | Pessimistic Duration | Estimated Duration | Variance | Standard Deviation
1 | Project management |  |  |  | 85 days | 200 days | 115 days | 34 | 5.83
1.1 |  | Planning |  |  | 35 days | 10
1.2 |  | Cost and schedule management
1.3 |  | Scope management
1.4 |  | Task management |  |  | 100 | 150
1.5 |  | Project office administration |  |  | 5 | 17
1.6 |  | Project communication
|  | Human resource management |  |  | 3 | 10
2 | Systems Engineering |  |  | 1 | 10 days | 35 days | 15 days | 6.25 | 2.5
2.1 |  | Technical planning |  |  | 2 | 7
2.2 |  | Technical supervision |  |  | 4 | 7
2.3 |  | Business requirements definition |  |  | 3 | 12
2.4 |  | System requirements definition
2.5 |  | System architecture & top level design |  |  | 6 | 9
3 | Software |  |  | 1,2 | 9 days | 30 days | 21 days | 12.25 | 3.5
3.1 |  | Software Design
3.1.2 |  |  | Software requirement specification |  | 3 | 5
3.1.3 |  |  | Software work package defintion
3.1.4 |  |  | Software prototyping |  | 4 | 7
3.1.5 |  |  | Software unit detailed design
3.2 |  | Software Build | Software unit coding |  | 2 | 5
3.2.1 |  |  | Software unit debugging
3.3 |  | Unit Testing | Unit test planning |  | 3 | 9
3.2.1 |  |  | Unit Test case preparation
3.2.2 |  |  | Unit test conduct |  | 2 | 4
3.2.3 |  |  | Unit test records
4 | Hardware |  |  | 2,3 | 5 days | 15 days | 10 days | 2.77 | 1.66
4.1 |  | Hardware requirements |  |  | 3 | 7
4.2 |  | Hardware system definition
4.3 |  | Hardware component selection |  |  | 4 | 3
4.4 |  | Hardware unit/component testing |  |  | 2 | 5
5 | Deliverables Management |  |  | 3 | 4 days | 12 days | 8 days | 1.77 | 1.33
5.1 |  | Deliverables Tracking |  |  | 2 | 6
5.2 |  | Deliverables production and packaging |  |  | 2 | 6
6 | System Test |  |  | 3 | 5 days | 18 days | 13 days | 4.69 | 2.16
6.1 |  | Module & subsytem testing |  |  | 6 | 8
6.2 |  | System integration testing |  |  | 2 | 4
6.3 |  | Acceptance testing |  |  | 3 | 7
6.4 |  | Defect classification, tracking & metrics
7 | Installation |  |  | 3,4 | 3 days | 10 days | 7 days | 1.36 | 1.16
7.1 |  | Installation planning |  |  | 7 | 9
7.2 |  | User support documentation
7.3 |  | User communication & training |  |  | 3 | 5
7.4 |  | Installaion managament and coordination
7.5 |  | Insallation testing and verification |  |  | 4 | 7
7.6 |  | Installation performance and monitoring
8 | Support Services |  |  | 7 | 2 days | 8 days | 6 days | 1 | 1
8.1 |  | Configuration management |  |  | 3 | 5
8.2 |  | Quality assurance
8.3 |  | Developement tools and utilities
8.4 |  | Developement upkeep |  |  | 5 | 8
8.5 |  | Internal product liaison
8.6 |  | Team techinical training
Project Paths
1 >2 >4>7>8 | 35+15+10+7+6 =73
1>3>7>8 | 35+21+7+6=69
1>3>5>6 | 35+21+13+8=77
CRITICAL PATH
1>3>5>6 | 77 Days