## Sheet1
Activity | Description | Immediate Predecessors | Optimistic Duration | Pessimistic Duration | Estimated Duration
A | Project management |  | 15 days | 50 days | 35 days
B | Systems Engineering | A | 10 days | 35 days | 15 days
C | Software | A,B | 9 days | 30 days | 21 days
D | Hardware | B,C | 5 days | 15 days | 10 days
E | Deliverables Management | C | 4 days | 12 days | 8 days
F | System Test | C | 5 days | 18 days | 13 days
G | Installation | C,D | 3 days | 10 days | 7 days
H | Support Services | G | 2 days | 8 days | 6 days
Project Paths
A >B >D>G>H | 35+15+10+7+6 =73
A>C>G>H | 35+21+7+6=69
A>C>E>F | 35+21+13+8=77
CRITICAL PATH
A>C>E>F | 77 Days
Standard Deviation = Square Root of Variance |  | σ = (P – O)/6
sd= (Pessimistic time - Optimistic time)/6
Project Activity Variance
Activity | Description | Immediate Predecessors | Optimistic Duration | Pessimistic Duration | Estimated Duration | Variance | Standard Deviation
A | Project management |  | 15 days | 50 days | 35 days | 34 | 5.83
B | Systems Engineering | A | 10 days | 35 days | 15 days | 6.25 | 2.5
C | Software | A,B | 9 days | 30 days | 21 days | 12.25 | 3.5
D | Hardware | B,C | 5 days | 15 days | 10 days | 2.77 | 1.66
E | Deliverables Management | C | 4 days | 12 days | 8 days | 1.77 | 1.33
F | System Test | C | 5 days | 18 days | 13 days | 4.69 | 2.16
G | Installation | C,D | 3 days | 10 days | 7 days | 1.36 | 1.16
H | Support Services | G | 2 days | 8 days | 6 days | 1 | 1
Probability of 90% project completion