## Sheet1
Activity | Description |  |  | Immediate Predecessors | Optimistic Duration | Pessimistic Duration | Estimated Duration | Variance | Standard Deviation
A | Project management |  |  |  | 15 days | 50 days | 35 days | 34 | 5.83
|  | Planning |  |  | 5 | 10
Cost and schedule management
Scope management
|  | Task management |  |  | 2 | 13
|  | Project office administration |  |  | 5 | 17
Project communication
|  | Human resource management |  |  | 3 | 10
B | Systems Engineering |  |  | A | 10 days | 35 days | 15 days | 6.25 | 2.5
|  | Technical planning |  |  | 2 | 7
|  | Technical supervision |  |  | 2 | 7
|  | Business requirements definition |  |  | 3 | 12
System requirements definition
|  | System architecture & top level design |  |  | 3 | 9
C | Software |  |  | A,B | 9 days | 30 days | 21 days | 12.25 | 3.5
Software Design
|  |  | Software requirement specification |  | 1 | 5
Software work package defintion
|  |  | Software prototyping |  | 2 | 7
Software unit detailed design
|  | Software Build | Software unit coding |  | 2 | 5
Software unit debugging
|  | Unit Testing | Unit test planning |  | 2 | 9
Unit Test case preparation
|  |  | Unit test conduct |  | 2 | 4
Unit test records
D | Hardware |  |  | B,C | 5 days | 15 days | 10 days | 2.77 | 1.66
|  | Hardware requirements |  |  | 2 | 7
Hardware system definition
|  | Hardware component selection |  |  | 1 | 3
|  | Hardware unit/component testing |  |  | 2 | 5
E | Deliverables Management |  |  | C | 4 days | 12 days | 8 days | 1.77 | 1.33
|  | Deliverables Tracking |  |  | 2 | 6
|  | Deliverables production and packaging |  |  | 2 | 6
F | System Test |  |  | C | 5 days | 18 days | 13 days | 4.69 | 2.16
|  | Module & subsytem testing |  |  | 1 | 7
|  | System integration testing |  |  | 1 | 4
|  | Acceptance testing |  |  | 1 | 7
Defect classification, tracking & metrics
G | Installation |  |  | C,D | 3 days | 10 days | 7 days | 1.36 | 1.16
|  | Installation planning |  |  | 1 | 3
User support documentation
|  | User communication & training |  |  | 1 | 3
Installaion managament and coordination
|  | Insallation testing and verification |  |  | 1 | 4
Installation performance and monitoring
H | Support Services |  |  | G | 2 days | 8 days | 6 days | 1 | 1
|  | Configuration management |  |  | 1 | 5
Quality assurance
Developement tools and utilities
|  | Developement upkeep |  |  | 1 | 3
Internal product liaison
Team techinical training
Project Paths
A >B >D>G>H | 35+15+10+7+6 =73
A>C>G>H | 35+21+7+6=69
A>C>E>F | 35+21+13+8=77
CRITICAL PATH
A>C>E>F | 77 Days
Standard Deviation = Square Root of Variance |  |  |  | σ = (P – O)/6
sd= (Pessimistic time - Optimistic time)/6
Project Activity Variance
Activity | Description |  |  | Immediate Predecessors | Optimistic Duration | Pessimistic Duration | Estimated Duration
A | Project management |  |  |  | 15 days | 50 days | 35 days
B | Systems Engineering |  |  | A | 10 days | 35 days | 15 days
C | Software |  |  | A,B | 9 days | 30 days | 21 days
D | Hardware |  |  | B,C | 5 days | 15 days | 10 days
E | Deliverables Management |  |  | C | 4 days | 12 days | 8 days
F | System Test |  |  | C | 5 days | 18 days | 13 days
G | Installation |  |  | C,D | 3 days | 10 days | 7 days
H | Support Services |  |  | G | 2 days | 8 days | 6 days
Probability of 90% project completion