This section outlines the roll out of the project plan.

Plan:

Phase I:	Emergency Department Documentation and Audit

Phase II:	Establish a Comprehensive Query Process

Phase III:	Determine and Implement CDI Program Metric Reporting

Phase IV:	Perform CDI program audits, analyze data and establish benchmarks

Phase V:	Identify potential compliance/ethical issues and implement corrective plans

Phase VI:	Establish ongoing education based on regulatory changes and audit findings

Emergency Department Documentation and Audit

- Secure the data

- Review the ED records

- Analyze components

- Compile results

Establish a Comprehensive Query Process

- Review the query process in the EHR

- A formed committee will focus on the query policy and procedures and query templates

Determine and Implement CDI Program Metric Reporting

- Review and analyze which CDI reports are most useful to the staff

- Develop a report for administration and physician leadership relating to query answer rate

- Present the query report

- Propose a corrective action plans and performance benchmarks for any query response issues

Perform CDI program audits, analyze data and establish benchmarks

- Establish targets for potential compliance issues

- CDI perform audits of queries

- Develop policy/procedures for potential fraud and abuse

Identify potential compliance/ethical issues and implement corrective action plans

- Identify areas for potential compliance issues

- Form a team to review the compliance target areas

- Identify issues

- Propose corrective action plan

Establish ongoing physician and staff education based on regulatory changes and audit findings

- Review audit findings

- Develop education plans and provide feedback for CDI and Physicians